## ENTREGABLES
objetivo: | lograr la implementación de todo el programa en 8 meses
quien va a ganar: | menor costo
1 | Tablero donde se vea el plan de trabajo general inicio - fin del programa
2 | tablero donde se vea el plan de trabajo por site
3 | tabla de uso de recursos por sitio y general para el programa. Quiero poder modificar esa tabla
4 | poder guardar el escenario
5 | que me de un resumen de costos para el programa (por escenario), costo por site, por tipo de recurso
rubrica de calificación |  | Maxima | Ejemplo
|  | 100% | 84.38%
| 8 meses + menor costo | 50% | 50%
| Rúbrica | 50% | 34.38%
|  | Maxima | Ejemplo
| Dashboard principal | 4 | 2
| Guardar y comparar escenarios | 4 | 3
| Explicacion y entendimiento de cada pestaña del excel | 4 | 3
| Calidad de la información. Correcta, bien etiquetada, sin basura ni errores. | 2 | 1
| Visual / UI. Limpio, con jerarquía y legible. | 2 | 2
|  | 16 | 11
|  | 50% | 34.38%

## Sites Master
Country | Brewery | Cluster | Capacity (Mio HL) | Production (Mio HL) | Distribution Volume (K HL) | Line Capacity | Production Lines | # Warehouses | Warehouse Area | Occupation LV | Aisles Identification | Box Identification | Control Tower | T2/MKP/KA | Forklifts in Logistics | HC Forklifts | WIFI State | Tablets | Counting Devices
Mexico | Site 01 | 2 | 3.72 | 1.43 | 6400 | 38.44% | 3 | 1 | 9100 | 81.5% | 89% | Yes | No | No | 18 | 38 | 85% | 15 | 5
Mexico | Site 02 | 2 | 6.46 | 4.77 | 11160 | 73.84% | 6 | 2 | 15572 | 94% | 0% | No | No | No | 30 | 90 | 0% | 29 | 6
Mexico | Site 03 | 2 | 6.46 | 4.77 | 11160 | 73.84% | 6 | 2 | 15572 | 94% | 0% | No | No | No | 30 | 90 | 0% | 29 | 6
Mexico | Site 04 | 2 | 6.59 | 4.58 | 11520 | 69.5% | 5 | 2 | 17742 | 78% | 0% | No | Yes | No | 37 | 80 | 0% | 15 | 4
Mexico | Site 05 | 3 | 2.75 | 2.12 | 6848 | 77.09% | 2 | 3 | 5239 | 85.5% | 90% | Yes | No | Yes | 14 | 42 | 0% | 14 | 4
Mexico | Site 06 | 1 | 13.2 | 12.19 | 29946 | 92.35% | 9 | 2 | 36333 | 100% | 93% | Yes | Yes | Yes | 76 | 213 | 0% | 85 | 8
Mexico | Site 07 | 2 | 4.77 | 3.82 | 9900 | 80.08% | 4 | 1 | 14897 | 105% | 0% | No | No | Yes | 32 | 75 | 0% | 32 | 6
Colombia | Site 08 | 1 | 14.2623 | 14.2215 | 11189 | 99.71% | 3 | 1 | 28576 | 104% | 100% | Yes | Yes | Yes | 32 | 117 | 100% | 40 | 5
Colombia | Site 09 | 2 | 7.9589 | 3.0929 | 1822.3038 | 38.86% | 4 | 1 | 14097 | 88% | 50% | Yes | Yes | Yes | 10 | 32 | 70% | 20 | 4
Colombia | Site 10 | 1 | 13.6895 | 10.3165 | 11164.5596 | 75.36% | 10 | 4 | 13978 | 96% | 80% | No | Yes | Yes | 62 | 169 | 50% | 55 | 7
Colombia | Site 11 | 3 | 3.9804 | 3.4123 | 2911.3283 | 85.73% | 4 | 3 | 4684 | 84% | 80% | No | No | No | 17 | 42 | 60% | 16 | 3
Colombia | Site 12 | 4 | 2.1682 | 0.72308 | 699.0703 | 33.35% | 2 | 1 | 3797 | 80% | 80% | No | No | No | 4 | 15 | 70% | 5 | 3
Colombia | Site 13 | 1 | 30.3682 | 20.9553 | 23650.2134 | 69% | 14 | 2 | 85322 | 108% | 80% | Yes | Yes | Yes | 100 | 345 | 60% | 135 | 15
Colombia | Site 14 | 1 | 13.6373 | 10.6181 | 11442.7306 | 77.86% | 11 | 1 | 69016 | 88% | 80% | No | Yes | No | 52 | 166 | 50% | 60 | 6
Colombia | Site 15 | 2 | 5.0028 | 4.509 | 4946.467 | 90.13% | 5 | 3 | 9601 | 105% | 60% | No | Yes | No | 19 | 54 | 70% | 18 | 4

## Financials (USD)
Country | Brewery | Benefits per month | Implementation Costs | Devices | Forklift Structure | Warehouse Signage | Labels | Costs without Labelers & WiFi | Label Printers / Labelers | Manual Labeling | WiFi Full | WiFi Full Optimized | WiFi Prioritized
Mexico | Site 01 | 18511 | 15000 | 0 | 6668.7957 | 11370.3713 | 14425.1534 | 47464.3204 | 7144.76 | 0 | 44451 | 43451 | 0
Mexico | Site 02 | 26878 | 15000 | 70212.869 | 9262.2162 | 27796.938 | 21152.7918 | 143424.8151 | 81930.072 | 142702.7027 | 287249 | 220687 | 110343.5
Mexico | Site 03 | 61087 | 25000 | 84255.4429 | 11114.6595 | 23591.8332 | 18886.4213 | 162848.3568 | 212307.9 | 259459.4595 | 378909 | 157740 | 112671.4286
Mexico | Site 04 | 70898 | 25000 | 103915.0462 | 13708.0801 | 44202.7663 | 19286.8134 | 206112.706 | 184000.18 | 220540.5405 | 411279 | 368914 | 230571.25
Mexico | Site 05 | 14809 | 15000 | 0 | 5927.8184 | 10505.1615 | 11709.5812 | 43142.561 | 73600.072 | 103783.7838 | 219880 | 206497 | 77436.375
Mexico | Site 06 | 76636 | 35000 | 213447.1219 | 28157.1374 | 43677.8758 | 49482.4237 | 369764.5588 | 302730.288 | 376216.2162 | 523835 | 297466 | 220345.1852
Mexico | Site 07 | 30543 | 25000 | 98298.0167 | 12967.1028 | 39945.6344 | 13220.4949 | 189431.2487 | 147200.144 | 181621.6216 | 277152 | 123137 | 94720.7692
Colombia | Site 08 | 70420 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0
Colombia | Site 09 | 15920 | 15000 | 0 | 3600 | 12547 | 3600 | 34747 | 0 | 0 | 133781 | 115803 | 100862
Colombia | Site 10 | 90320 | 25000 | 0 | 15600 | 57883 | 8100 | 106583 | 308459.6755 | 0 | 487872 | 364795 | 154945.835
Colombia | Site 11 | 24480 | 15000 | 0 | 5560 | 15273 | 4500 | 40333 | 176263 | 0 | 180753 | 185549 | 94573.8118
Colombia | Site 12 | 10180 | 5000 | 0 | 1440 | 3746 | 1800 | 11986 | 88131 | 0 | 116598 | 73392 | 43642.3158
Colombia | Site 13 | 109140 | 50000 | 369489 | 44000 | 73532 | 20700 | 557721 | 1189773 | 0 | 333663 | 267903 | 136549.4177
Colombia | Site 14 | 56820 | 35000 | 0 | 18560 | 58580 | 9000 | 121140 | 925379 | 0 | 319639 | 286043 | 121496.1046
Colombia | Site 15 | 27560 | 15000 | 0 | 5320 | 20351 | 3600 | 44271 | 88131 | 0 | 139767 | 134417 | 79930.6351

## Resource Master
Role | Work Mode | Can Multitask | Internal or External | Fixed or Flexible Cost | Average Monthly Cost (MXN) | Actual | Escenario 1
Solution Architect | Remote | Yes | Internal | Fixed | 36000 | 1 | 5 | Go Live | Post
Warehouse Manager Org A | Hybrid | Yes | Internal | Fixed | 35000 | 1 | 5
Project Manager Country B | Hybrid | Partial | Internal | Fixed | 25000 | 1 | 5
Project Manager Country A | Hybrid | Partial | Internal | Fixed | 25000 | 1 | 5
Change Management Lead | Onsite | No | Internal | Fixed | 16000 | 1 | 5
Change Management Lead | Onsite | No | External | Fixed | 16000 | 1 | 5
Infrastructure Lead | Onsite | No | Internal | Fixed | 42000 | 1 | 5
Infrastructure Lead | Onsite | No | External | Flexible | 43000 | 1 | 5
Functional Lead | Onsite | No | Internal | Fixed | 35000 | 1 | 5
Functional Lead | Onsite | No | External | Flexible | 35000 | 1 | 5
SAP Integrations Lead | Remote | Yes | Internal | Fixed | 62000 | 1 | 5
SAP Integrations Specialist | Remote | Yes | Internal | Flexible | 55000 | 1 | 5
Azure Lead | Remote | Yes | Internal | Fixed | 48000 | 1 | 5
Azure Specialist | Remote | Yes | Internal | Flexible | 45000 | 1 | 5
Testing Lead | Remote | Partial | Internal | Flexible | 35000 | 1 | 5
Trainers | Onsite | No | External | Flexible | 28000 | 1 | 5
Functional Lead Vendor A | Remote | Yes | External | Flexible | 36000 | 2 | 5
Support Lead | Remote | Yes | External | Flexible | 22000 | 2 | 5

## Implementation Phases
Cluster | Phase | Sequence | Deployment Maturity | Duration in Weeks
1 | Site Readiness | 1 | A | 5
1 | Design Adaptation | 2 | A | 2
1 | Functional Review | 3 | A | 1
1 | UAT | 4 | A | 2
1 | Training | 5 | A | 3
1 | DIALT | 6 | A | 1
1 | Go Live | 7 | A | 1
1 | Hypercare | 8 | A | 4
2 | Site Readiness | 1 | A | 4
2 | Design Adaptation | 2 | A | 1
2 | Functional Review | 3 | A | 1
2 | UAT | 4 | A | 2
2 | Training | 5 | A | 2
2 | DIALT | 6 | A | 1
2 | Go Live | 7 | A | 1
2 | Hypercare | 8 | A | 4
3 | Site Readiness | 1 | A | 4
3 | Design Adaptation | 2 | A | 1
3 | Functional Review | 3 | A | 1
3 | UAT | 4 | A | 1
3 | Training | 5 | A | 2
3 | DIALT | 6 | A | 1
3 | Go Live | 7 | A | 1
3 | Hypercare | 8 | A | 4
4 | Site Readiness | 1 | A | 2
4 | Design Adaptation | 2 | A | 0
4 | Functional Review | 3 | A | 1
4 | UAT | 4 | A | 1
4 | Training | 5 | A | 1
4 | DIALT | 6 | A | 1
4 | Go Live | 7 | A | 1
4 | Hypercare | 8 | A | 3
1 | Site Readiness | 1 | B | 4
1 | Design Adaptation | 2 | B | 1
1 | Functional Review | 3 | B | 1
1 | UAT | 4 | B | 1
1 | Training | 5 | B | 2
1 | DIALT | 6 | B | 1
1 | Go Live | 7 | B | 1
1 | Hypercare | 8 | B | 4
2 | Site Readiness | 1 | B | 4
2 | Design Adaptation | 2 | B | 1
2 | Functional Review | 3 | B | 1
2 | UAT | 4 | B | 1
2 | Training | 5 | B | 2
2 | DIALT | 6 | B | 1
2 | Go Live | 7 | B | 1
2 | Hypercare | 8 | B | 4
3 | Site Readiness | 1 | B | 4
3 | Design Adaptation | 2 | B | 1
3 | Functional Review | 3 | B | 1
3 | UAT | 4 | B | 1
3 | Training | 5 | B | 2
3 | DIALT | 6 | B | 1
3 | Go Live | 7 | B | 1
3 | Hypercare | 8 | B | 4
4 | Site Readiness | 1 | B | 2
4 | Design Adaptation | 2 | B | 0
4 | Functional Review | 3 | B | 1
4 | UAT | 4 | B | 1
4 | Training | 5 | B | 1
4 | DIALT | 6 | B | 1
4 | Go Live | 7 | B | 1
4 | Hypercare | 8 | B | 3

## Phase-Resource Allocation
Cluster | Phase | Role | Capacity Consumption
1 | Site Readiness | Infrastructure Lead | 100%
1 | Site Readiness | SAP Integrations Lead | 50%
1 | Design Adaptation | Solution Architect | 100%
1 | Design Adaptation | SAP Integrations Lead | 50%
1 | Design Adaptation | SAP Integrations Specialist | 50%
1 | Design Adaptation | Azure Lead | 50%
1 | Design Adaptation | Azure Specialist | 50%
1 | Design Adaptation | Testing Lead | 100%
1 | Design Adaptation | Functional Lead | 100%
1 | Design Adaptation | Trainers | 100%
1 | Design Adaptation | Infrastructure Lead | 100%
1 | Design Adaptation | Functional Lead Vendor A | 100%
1 | Functional Review | Solution Architect | 50%
1 | Functional Review | Change Management Lead | 100%
1 | Functional Review | SAP Integrations Lead | 50%
1 | Functional Review | SAP Integrations Specialist | 50%
1 | Functional Review | Azure Lead | 50%
1 | Functional Review | Azure Specialist | 50%
1 | Functional Review | Testing Lead | 50%
1 | Functional Review | Functional Lead | 100%
1 | Functional Review | Trainers | 100%
1 | UAT | Solution Architect | 50%
1 | UAT | Change Management Lead | 100%
1 | UAT | SAP Integrations Lead | 50%
1 | UAT | SAP Integrations Specialist | 50%
1 | UAT | Azure Lead | 50%
1 | UAT | Azure Specialist | 50%
1 | UAT | Testing Lead | 50%
1 | UAT | Functional Lead | 100%
1 | UAT | Trainers | 100%
1 | Training | Change Management Lead | 100%
1 | Training | Trainers | 100%
1 | DIALT | Solution Architect | 50%
1 | DIALT | Change Management Lead | 100%
1 | DIALT | Azure Lead | 75%
1 | DIALT | Azure Specialist | 75%
1 | DIALT | Functional Lead | 100%
1 | DIALT | Trainers | 100%
1 | DIALT | Functional Lead Vendor A | 100%
1 | Go Live | Solution Architect | 100%
1 | Go Live | Change Management Lead | 100%
1 | Go Live | SAP Integrations Lead | 100%
1 | Go Live | SAP Integrations Specialist | 100%
1 | Go Live | Azure Lead | 100%
1 | Go Live | Azure Specialist | 100%
1 | Go Live | Functional Lead | 100%
1 | Go Live | Trainers | 100%
1 | Go Live | Infrastructure Lead | 100%
1 | Go Live | Functional Lead Vendor A | 100%
1 | Hypercare | Solution Architect | 50%
1 | Hypercare | Change Management Lead | 100%
1 | Hypercare | SAP Integrations Lead | 50%
1 | Hypercare | SAP Integrations Specialist | 50%
1 | Hypercare | Azure Lead | 50%
1 | Hypercare | Azure Specialist | 50%
1 | Hypercare | Functional Lead | 100%
1 | Hypercare | Functional Lead | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Trainers | 100%
1 | Hypercare | Infrastructure Lead | 100%
1 | Hypercare | Functional Lead Vendor A | 50%
2 | Site Readiness | Infrastructure Lead | 100%
2 | Site Readiness | SAP Integrations Lead | 50%
2 | Design Adaptation | Solution Architect | 100%
2 | Design Adaptation | SAP Integrations Lead | 50%
2 | Design Adaptation | SAP Integrations Specialist | 50%
2 | Design Adaptation | Azure Lead | 50%
2 | Design Adaptation | Azure Specialist | 50%
2 | Design Adaptation | Testing Lead | 100%
2 | Design Adaptation | Functional Lead | 100%
2 | Design Adaptation | Trainers | 100%
2 | Design Adaptation | Infrastructure Lead | 100%
2 | Design Adaptation | Functional Lead Vendor A | 100%
2 | Functional Review | Solution Architect | 50%
2 | Functional Review | Change Management Lead | 100%
2 | Functional Review | SAP Integrations Lead | 50%
2 | Functional Review | SAP Integrations Specialist | 50%
2 | Functional Review | Azure Lead | 50%
2 | Functional Review | Azure Specialist | 50%
2 | Functional Review | Testing Lead | 50%
2 | Functional Review | Functional Lead | 100%
2 | Functional Review | Trainers | 100%
2 | UAT | Solution Architect | 50%
2 | UAT | Change Management Lead | 100%
2 | UAT | SAP Integrations Lead | 50%
2 | UAT | SAP Integrations Specialist | 50%
2 | UAT | Azure Lead | 50%
2 | UAT | Azure Specialist | 50%
2 | UAT | Testing Lead | 50%
2 | UAT | Functional Lead | 100%
2 | UAT | Trainers | 100%
2 | Training | Change Management Lead | 100%
2 | Training | Trainers | 100%
2 | DIALT | Solution Architect | 50%
2 | DIALT | Change Management Lead | 100%
2 | DIALT | Azure Lead | 75%
2 | DIALT | Azure Specialist | 75%
2 | DIALT | Functional Lead | 100%
2 | DIALT | Trainers | 100%
2 | DIALT | Functional Lead Vendor A | 100%
2 | Go Live | Solution Architect | 100%
2 | Go Live | Change Management Lead | 100%
2 | Go Live | SAP Integrations Lead | 100%
2 | Go Live | SAP Integrations Specialist | 100%
2 | Go Live | Azure Lead | 100%
2 | Go Live | Azure Specialist | 100%
2 | Go Live | Functional Lead | 100%
2 | Go Live | Trainers | 100%
2 | Go Live | Infrastructure Lead | 100%
2 | Go Live | Functional Lead Vendor A | 100%
2 | Hypercare | Solution Architect | 50%
2 | Hypercare | Change Management Lead | 100%
2 | Hypercare | SAP Integrations Lead | 50%
2 | Hypercare | SAP Integrations Specialist | 50%
2 | Hypercare | Azure Lead | 50%
2 | Hypercare | Azure Specialist | 50%
2 | Hypercare | Functional Lead | 100%
2 | Hypercare | Functional Lead | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Trainers | 100%
2 | Hypercare | Infrastructure Lead | 100%
2 | Hypercare | Functional Lead Vendor A | 50%
3 | Site Readiness | Infrastructure Lead | 100%
3 | Site Readiness | SAP Integrations Lead | 50%
3 | Design Adaptation | Solution Architect | 100%
3 | Design Adaptation | SAP Integrations Lead | 50%
3 | Design Adaptation | SAP Integrations Specialist | 50%
3 | Design Adaptation | Azure Lead | 50%
3 | Design Adaptation | Azure Specialist | 50%
3 | Design Adaptation | Testing Lead | 100%
3 | Design Adaptation | Functional Lead | 100%
3 | Design Adaptation | Trainers | 100%
3 | Design Adaptation | Infrastructure Lead | 100%
3 | Design Adaptation | Functional Lead Vendor A | 100%
3 | Functional Review | Solution Architect | 50%
3 | Functional Review | Change Management Lead | 100%
3 | Functional Review | SAP Integrations Lead | 50%
3 | Functional Review | SAP Integrations Specialist | 50%
3 | Functional Review | Azure Lead | 50%
3 | Functional Review | Azure Specialist | 50%
3 | Functional Review | Testing Lead | 50%
3 | Functional Review | Functional Lead | 100%
3 | Functional Review | Trainers | 100%
3 | UAT | Solution Architect | 50%
3 | UAT | Change Management Lead | 100%
3 | UAT | SAP Integrations Lead | 50%
3 | UAT | SAP Integrations Specialist | 50%
3 | UAT | Azure Lead | 50%
3 | UAT | Azure Specialist | 50%
3 | UAT | Testing Lead | 50%
3 | UAT | Functional Lead | 100%
3 | UAT | Trainers | 100%
3 | Training | Change Management Lead | 100%
3 | Training | Trainers | 100%
3 | DIALT | Solution Architect | 50%
3 | DIALT | Change Management Lead | 100%
3 | DIALT | Azure Lead | 75%
3 | DIALT | Azure Specialist | 75%
3 | DIALT | Functional Lead | 100%
3 | DIALT | Trainers | 100%
3 | DIALT | Functional Lead Vendor A | 100%
3 | Go Live | Solution Architect | 100%
3 | Go Live | Change Management Lead | 100%
3 | Go Live | SAP Integrations Lead | 100%
3 | Go Live | SAP Integrations Specialist | 100%
3 | Go Live | Azure Lead | 100%
3 | Go Live | Azure Specialist | 100%
3 | Go Live | Functional Lead | 100%
3 | Go Live | Trainers | 100%
3 | Go Live | Infrastructure Lead | 100%
3 | Go Live | Functional Lead Vendor A | 100%
3 | Hypercare | Solution Architect | 50%
3 | Hypercare | Change Management Lead | 100%
3 | Hypercare | SAP Integrations Lead | 50%
3 | Hypercare | SAP Integrations Specialist | 50%
3 | Hypercare | Azure Lead | 50%
3 | Hypercare | Azure Specialist | 50%
3 | Hypercare | Functional Lead | 100%
3 | Hypercare | Functional Lead | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Trainers | 100%
3 | Hypercare | Infrastructure Lead | 100%
3 | Hypercare | Functional Lead Vendor A | 50%

## 00_README
SIMULADOR WMS - GUIA DEL ARCHIVO
QUE ES ESTE ARCHIVO
Simulador de escenarios para la implementacion de un programa WMS en 15 sites (7 en Mexico, 8 en Colombia). Construido sobre las pestanas originales del archivo (ENTREGABLES, Sites Master, Financials (USD), Resource Master, Implementation Phases, Phase-Resource Allocation), que no fueron alteradas.
Todo el simulador es 100% formulas: no hay valores fijos que representen resultados. Cambiar cualquier input en 01_INPUTS recalcula en cadena el cronograma (02_SCHEDULE), los recursos (03_RESOURCES), los costos (04_COSTS), el tablero (05_DASHBOARD), la vista por site (06_SITE_VIEW) y la comparacion de escenarios (07_SCENARIOS).
RELACION ENTRE LAS PESTANAS ORIGINALES
Sites Master.Cluster + 01_INPUTS.Deployment Maturity -> Implementation Phases (Cluster, Phase, Deployment Maturity) -> Duration in Weeks por fase.
Sites Master.Cluster -> Phase-Resource Allocation (Cluster, Phase) -> Role + Capacity Consumption (recursos requeridos por fase).
Phase-Resource Allocation.Role -> Resource Master.Role (sumando las variantes Interno/Externo del mismo rol) -> Average Monthly Cost (MXN) y headcount disponible (Actual / Escenario 1).
Sites Master.Brewery (nombre del site) -> Financials (USD).Brewery -> Benefits per month, Implementation Costs, Devices, Forklift Structure, Warehouse Signage, Labels (suman 'Costs without Labelers & WiFi'), mas las opciones alternativas de etiquetado (Label Printers/Labelers o Manual Labeling) y de WiFi (Full, Full Optimized, Prioritized) que se eligen en 01_INPUTS.
ENTREGABLES define el objetivo (8 meses) y el criterio de exito (menor costo entre los que cumplen); ambos estan parametrizados en 01_INPUTS y en la regla de recomendacion de 07_SCENARIOS.
FLUJO DE USO
1) Ajuste los parametros en 01_INPUTS (nombre del escenario, fecha de inicio, Deployment Maturity, sites en paralelo, fuente de recursos, metodo de etiquetado, estrategia de WiFi, prioridad de sites, recursos disponibles por rol).
2) Revise 02_SCHEDULE para ver el cronograma resultante por site y fase.
3) Revise 03_RESOURCES para ver la utilizacion semanal por rol y los cuellos de botella.
4) Revise 04_COSTS para ver el costo por site, por recurso y el payback.
5) Revise 05_DASHBOARD para el resumen ejecutivo y el Gantt general contra la meta de 8 meses.
6) Use 06_SITE_VIEW para inspeccionar el detalle de un site especifico.
7) Cuando el escenario le sirva de referencia, copie la fila 'ESCENARIO ACTUAL' de 07_SCENARIOS y peguela como VALORES en una fila de 'Escenario guardado' para compararla contra otros escenarios.
SUPUESTOS Y DECISIONES DOCUMENTADAS
Paralelismo de sites: el archivo original no trae un algoritmo de nivelacion de recursos, asi que se modelo con una regla de 'N sitios en paralelo' (N = input editable 'Max. Sites en paralelo'). Los sites arrancan en el orden de prioridad definido en 01_INPUTS y cada uno inicia apenas se libera un cupo. El usuario ajusta N y observa el semaforo de utilizacion en 03_RESOURCES para encontrar un balance razonable; no es un optimizador automatico de recursos.
Cluster 4 / Site 12: no tiene filas en 'Phase-Resource Allocation' en el archivo original. Su demanda de recursos se calcula en 0 en 03_RESOURCES; no se inventaron datos para cubrir ese vacio.
Monedas: los costos de sites (Financials (USD)) estan en USD y los costos de recursos (Resource Master) estan en MXN en los datos originales, sin tipo de cambio provisto. Por eso se muestran y sumarizan por separado en 04_COSTS, y el payback usa unicamente los montos en USD (implementacion vs beneficio mensual).
Costo por recurso: se asume que cada recurso disponible esta contratado durante toda la duracion del programa (no hay un calendario de asignacion individual en el archivo original). Cuando un rol tiene variantes Interno/Externo con costos distintos (ej. Infrastructure Lead), se usa el promedio simple de esos costos ya que 'Disponible' agrupa ambas variantes en un solo headcount.
Guardado de escenarios: el archivo se entrega en formato .xlsx (sin macros), por lo que 'guardar un escenario' es un copiar y pegar como valores de la fila en vivo hacia una fila de escenario guardado en 07_SCENARIOS, en vez de un boton automatico.
Matriz de utilizacion semanal: se modelaron 150 semanas (~2.9 anios) para cubrir escenarios razonables de paralelismo. Si 'Duracion total (semanas)' en 02_SCHEDULE supera 150 (por ejemplo con Max. Sites en paralelo = 1), la matriz de 03_RESOURCES no cubrira todas las semanas del programa.
MAPA DE PESTANAS NUEVAS
01_INPUTS: todos los parametros editables del escenario (celdas azules).
02_SCHEDULE: cronograma calculado por site y fase (fechas, semanas, secuencia).
03_RESOURCES: disponibilidad vs demanda semanal por rol, semaforos y cuellos de botella.
04_COSTS: costo por site (USD), costo por recurso (MXN), beneficio y payback.
05_DASHBOARD: panel ejecutivo con KPIs, semaforo y Gantt general contra la meta de 8 meses.
06_SITE_VIEW: selector de site con su informacion, cronograma, costos, recursos y Gantt de fases.
07_SCENARIOS: tabla comparativa de escenarios y la recomendacion (cumple 8 meses + menor costo).

## 01_INPUTS
ZONA DE CALCULO INTERNO (listas de validacion) - no editar manualmente
SIMULADOR WMS - 01_INPUTS (parametros editables del escenario) |  |  |  | Deployment Maturity | Roles unicos | Fuente recursos | Metodo etiquetado | Estrategia WiFi
Las celdas en AZUL son editables. Cambiar cualquiera de estos valores recalcula todo el simulador (Schedule, Resources, Costs, Dashboard, Scenarios). |  |  |  | A | Solution Architect | Actual | Label Printers / Labelers | WiFi Full
|  |  |  | B | Warehouse Manager Org A | Escenario 1 | Manual Labeling | WiFi Full Optimized
PARAMETROS GENERALES DEL ESCENARIO |  |  |  |  | Project Manager Country B |  |  | WiFi Prioritized
Nombre del escenario | Escenario Base |  |  |  | Project Manager Country A
Fecha de inicio del programa | 2026-08-17 |  |  |  | Change Management Lead
Deployment Maturity (A o B, fuente: Implementation Phases) | A |  |  |  | Infrastructure Lead
Max. Sites en paralelo (palanca de paralelismo) | 3 |  |  |  | Functional Lead
Fuente de recursos disponibles (Resource Master) | Actual |  |  |  | SAP Integrations Lead
Metodo de etiquetado (fuente: Financials (USD)) | Label Printers / Labelers |  |  |  | SAP Integrations Specialist
Estrategia de WiFi (fuente: Financials (USD)) | WiFi Full |  |  |  | Azure Lead
Objetivo de duracion del programa (meses, fuente: ENTREGABLES) | 8 |  |  |  | Azure Specialist
Testing Lead
RECURSOS DISPONIBLES POR ROL (fuente: Resource Master) |  |  |  |  | Trainers
Rol | Disponible (fuente seleccionada) | Ajuste manual (opcional) | Disponible usado en el simulador |  | Functional Lead Vendor A
Solution Architect | 1 |  | 1 |  | Support Lead
Warehouse Manager Org A | 1 |  | 1
Project Manager Country B | 1 |  | 1
Project Manager Country A | 1 |  | 1
Change Management Lead | 2 |  | 2
Infrastructure Lead | 2 |  | 2
Functional Lead | 2 |  | 2
SAP Integrations Lead | 1 |  | 1
SAP Integrations Specialist | 1 |  | 1
Azure Lead | 1 |  | 1
Azure Specialist | 1 |  | 1
Testing Lead | 1 |  | 1
Trainers | 1 |  | 1
Functional Lead Vendor A | 2 |  | 2
Support Lead | 2 |  | 2
SECUENCIA / PRIORIDAD DE SITES (fuente: Sites Master)
Site | Pais | Cluster | Prioridad (1=primero, editable)
Site 01 | Mexico | 2 | 1
Site 02 | Mexico | 2 | 2
Site 03 | Mexico | 2 | 3
Site 04 | Mexico | 2 | 4
Site 05 | Mexico | 3 | 5
Site 06 | Mexico | 1 | 6
Site 07 | Mexico | 2 | 7
Site 08 | Colombia | 1 | 8
Site 09 | Colombia | 2 | 9
Site 10 | Colombia | 1 | 10
Site 11 | Colombia | 3 | 11
Site 12 | Colombia | 4 | 12
Site 13 | Colombia | 1 | 13
Site 14 | Colombia | 1 | 14
Site 15 | Colombia | 2 | 15

## 02_SCHEDULE
SIMULADOR WMS - 02_SCHEDULE (cronograma por Site y Fase)
Duracion total (semanas): | 86 | Duracion total (meses): | 19.7929 | Fecha fin programa: | 2028-04-09 | Objetivo (meses): | 8 | Cumple objetivo? | NO CUMPLE |  |  | ZONA DE CALCULO: secuenciacion de sites por prioridad y paralelismo (no editar)
Site | Pais | Cluster | Deployment Maturity | Fase | Secuencia | Duracion (semanas) | Fecha Inicio | Fecha Fin | Semana Inicio | Semana Fin | Key (uso interno 03_RESOURCES) | Prioridad | Site | Cluster | Duracion total site (sem) | Inicio Site | Fin Site
Site 01 | Mexico | 2 | A | Site Readiness | 1 | 4 | 2026-08-17 | 2026-09-13 | 1 | 4 | Site 01¦Site Readiness | 1 | Site 01 | 2 | 16 | 2026-08-17 | 2026-12-06
Site 01 | Mexico | 2 | A | Design Adaptation | 2 | 1 | 2026-09-14 | 2026-09-20 | 5 | 5 | Site 01¦Design Adaptation | 2 | Site 02 | 2 | 16 | 2026-08-17 | 2026-12-06
Site 01 | Mexico | 2 | A | Functional Review | 3 | 1 | 2026-09-21 | 2026-09-27 | 6 | 6 | Site 01¦Functional Review | 3 | Site 03 | 2 | 16 | 2026-08-17 | 2026-12-06
Site 01 | Mexico | 2 | A | UAT | 4 | 2 | 2026-09-28 | 2026-10-11 | 7 | 8 | Site 01¦UAT | 4 | Site 04 | 2 | 16 | 2026-12-07 | 2027-03-28
Site 01 | Mexico | 2 | A | Training | 5 | 2 | 2026-10-12 | 2026-10-25 | 9 | 10 | Site 01¦Training | 5 | Site 05 | 3 | 15 | 2026-12-07 | 2027-03-21
Site 01 | Mexico | 2 | A | DIALT | 6 | 1 | 2026-10-26 | 2026-11-01 | 11 | 11 | Site 01¦DIALT | 6 | Site 06 | 1 | 19 | 2026-12-07 | 2027-04-18
Site 01 | Mexico | 2 | A | Go Live | 7 | 1 | 2026-11-02 | 2026-11-08 | 12 | 12 | Site 01¦Go Live | 7 | Site 07 | 2 | 16 | 2027-03-29 | 2027-07-18
Site 01 | Mexico | 2 | A | Hypercare | 8 | 4 | 2026-11-09 | 2026-12-06 | 13 | 16 | Site 01¦Hypercare | 8 | Site 08 | 1 | 19 | 2027-03-22 | 2027-08-01
Site 02 | Mexico | 2 | A | Site Readiness | 1 | 4 | 2026-08-17 | 2026-09-13 | 1 | 4 | Site 02¦Site Readiness | 9 | Site 09 | 2 | 16 | 2027-04-19 | 2027-08-08
Site 02 | Mexico | 2 | A | Design Adaptation | 2 | 1 | 2026-09-14 | 2026-09-20 | 5 | 5 | Site 02¦Design Adaptation | 10 | Site 10 | 1 | 19 | 2027-07-19 | 2027-11-28
Site 02 | Mexico | 2 | A | Functional Review | 3 | 1 | 2026-09-21 | 2026-09-27 | 6 | 6 | Site 02¦Functional Review | 11 | Site 11 | 3 | 15 | 2027-08-02 | 2027-11-14
Site 02 | Mexico | 2 | A | UAT | 4 | 2 | 2026-09-28 | 2026-10-11 | 7 | 8 | Site 02¦UAT | 12 | Site 12 | 4 | 10 | 2027-08-09 | 2027-10-17
Site 02 | Mexico | 2 | A | Training | 5 | 2 | 2026-10-12 | 2026-10-25 | 9 | 10 | Site 02¦Training | 13 | Site 13 | 1 | 19 | 2027-11-29 | 2028-04-09
Site 02 | Mexico | 2 | A | DIALT | 6 | 1 | 2026-10-26 | 2026-11-01 | 11 | 11 | Site 02¦DIALT | 14 | Site 14 | 1 | 19 | 2027-11-15 | 2028-03-26
Site 02 | Mexico | 2 | A | Go Live | 7 | 1 | 2026-11-02 | 2026-11-08 | 12 | 12 | Site 02¦Go Live | 15 | Site 15 | 2 | 16 | 2027-10-18 | 2028-02-06
Site 02 | Mexico | 2 | A | Hypercare | 8 | 4 | 2026-11-09 | 2026-12-06 | 13 | 16 | Site 02¦Hypercare
Site 03 | Mexico | 2 | A | Site Readiness | 1 | 4 | 2026-08-17 | 2026-09-13 | 1 | 4 | Site 03¦Site Readiness
Site 03 | Mexico | 2 | A | Design Adaptation | 2 | 1 | 2026-09-14 | 2026-09-20 | 5 | 5 | Site 03¦Design Adaptation
Site 03 | Mexico | 2 | A | Functional Review | 3 | 1 | 2026-09-21 | 2026-09-27 | 6 | 6 | Site 03¦Functional Review
Site 03 | Mexico | 2 | A | UAT | 4 | 2 | 2026-09-28 | 2026-10-11 | 7 | 8 | Site 03¦UAT
Site 03 | Mexico | 2 | A | Training | 5 | 2 | 2026-10-12 | 2026-10-25 | 9 | 10 | Site 03¦Training
Site 03 | Mexico | 2 | A | DIALT | 6 | 1 | 2026-10-26 | 2026-11-01 | 11 | 11 | Site 03¦DIALT
Site 03 | Mexico | 2 | A | Go Live | 7 | 1 | 2026-11-02 | 2026-11-08 | 12 | 12 | Site 03¦Go Live
Site 03 | Mexico | 2 | A | Hypercare | 8 | 4 | 2026-11-09 | 2026-12-06 | 13 | 16 | Site 03¦Hypercare
Site 04 | Mexico | 2 | A | Site Readiness | 1 | 4 | 2026-12-07 | 2027-01-03 | 17 | 20 | Site 04¦Site Readiness
Site 04 | Mexico | 2 | A | Design Adaptation | 2 | 1 | 2027-01-04 | 2027-01-10 | 21 | 21 | Site 04¦Design Adaptation
Site 04 | Mexico | 2 | A | Functional Review | 3 | 1 | 2027-01-11 | 2027-01-17 | 22 | 22 | Site 04¦Functional Review
Site 04 | Mexico | 2 | A | UAT | 4 | 2 | 2027-01-18 | 2027-01-31 | 23 | 24 | Site 04¦UAT
Site 04 | Mexico | 2 | A | Training | 5 | 2 | 2027-02-01 | 2027-02-14 | 25 | 26 | Site 04¦Training
Site 04 | Mexico | 2 | A | DIALT | 6 | 1 | 2027-02-15 | 2027-02-21 | 27 | 27 | Site 04¦DIALT
Site 04 | Mexico | 2 | A | Go Live | 7 | 1 | 2027-02-22 | 2027-02-28 | 28 | 28 | Site 04¦Go Live
Site 04 | Mexico | 2 | A | Hypercare | 8 | 4 | 2027-03-01 | 2027-03-28 | 29 | 32 | Site 04¦Hypercare
Site 05 | Mexico | 3 | A | Site Readiness | 1 | 4 | 2026-12-07 | 2027-01-03 | 17 | 20 | Site 05¦Site Readiness
Site 05 | Mexico | 3 | A | Design Adaptation | 2 | 1 | 2027-01-04 | 2027-01-10 | 21 | 21 | Site 05¦Design Adaptation
Site 05 | Mexico | 3 | A | Functional Review | 3 | 1 | 2027-01-11 | 2027-01-17 | 22 | 22 | Site 05¦Functional Review
Site 05 | Mexico | 3 | A | UAT | 4 | 1 | 2027-01-18 | 2027-01-24 | 23 | 23 | Site 05¦UAT
Site 05 | Mexico | 3 | A | Training | 5 | 2 | 2027-01-25 | 2027-02-07 | 24 | 25 | Site 05¦Training
Site 05 | Mexico | 3 | A | DIALT | 6 | 1 | 2027-02-08 | 2027-02-14 | 26 | 26 | Site 05¦DIALT
Site 05 | Mexico | 3 | A | Go Live | 7 | 1 | 2027-02-15 | 2027-02-21 | 27 | 27 | Site 05¦Go Live
Site 05 | Mexico | 3 | A | Hypercare | 8 | 4 | 2027-02-22 | 2027-03-21 | 28 | 31 | Site 05¦Hypercare
Site 06 | Mexico | 1 | A | Site Readiness | 1 | 5 | 2026-12-07 | 2027-01-10 | 17 | 21 | Site 06¦Site Readiness
Site 06 | Mexico | 1 | A | Design Adaptation | 2 | 2 | 2027-01-11 | 2027-01-24 | 22 | 23 | Site 06¦Design Adaptation
Site 06 | Mexico | 1 | A | Functional Review | 3 | 1 | 2027-01-25 | 2027-01-31 | 24 | 24 | Site 06¦Functional Review
Site 06 | Mexico | 1 | A | UAT | 4 | 2 | 2027-02-01 | 2027-02-14 | 25 | 26 | Site 06¦UAT
Site 06 | Mexico | 1 | A | Training | 5 | 3 | 2027-02-15 | 2027-03-07 | 27 | 29 | Site 06¦Training
Site 06 | Mexico | 1 | A | DIALT | 6 | 1 | 2027-03-08 | 2027-03-14 | 30 | 30 | Site 06¦DIALT
Site 06 | Mexico | 1 | A | Go Live | 7 | 1 | 2027-03-15 | 2027-03-21 | 31 | 31 | Site 06¦Go Live
Site 06 | Mexico | 1 | A | Hypercare | 8 | 4 | 2027-03-22 | 2027-04-18 | 32 | 35 | Site 06¦Hypercare
Site 07 | Mexico | 2 | A | Site Readiness | 1 | 4 | 2027-03-29 | 2027-04-25 | 33 | 36 | Site 07¦Site Readiness
Site 07 | Mexico | 2 | A | Design Adaptation | 2 | 1 | 2027-04-26 | 2027-05-02 | 37 | 37 | Site 07¦Design Adaptation
Site 07 | Mexico | 2 | A | Functional Review | 3 | 1 | 2027-05-03 | 2027-05-09 | 38 | 38 | Site 07¦Functional Review
Site 07 | Mexico | 2 | A | UAT | 4 | 2 | 2027-05-10 | 2027-05-23 | 39 | 40 | Site 07¦UAT
Site 07 | Mexico | 2 | A | Training | 5 | 2 | 2027-05-24 | 2027-06-06 | 41 | 42 | Site 07¦Training
Site 07 | Mexico | 2 | A | DIALT | 6 | 1 | 2027-06-07 | 2027-06-13 | 43 | 43 | Site 07¦DIALT
Site 07 | Mexico | 2 | A | Go Live | 7 | 1 | 2027-06-14 | 2027-06-20 | 44 | 44 | Site 07¦Go Live
Site 07 | Mexico | 2 | A | Hypercare | 8 | 4 | 2027-06-21 | 2027-07-18 | 45 | 48 | Site 07¦Hypercare
Site 08 | Colombia | 1 | A | Site Readiness | 1 | 5 | 2027-03-22 | 2027-04-25 | 32 | 36 | Site 08¦Site Readiness
Site 08 | Colombia | 1 | A | Design Adaptation | 2 | 2 | 2027-04-26 | 2027-05-09 | 37 | 38 | Site 08¦Design Adaptation
Site 08 | Colombia | 1 | A | Functional Review | 3 | 1 | 2027-05-10 | 2027-05-16 | 39 | 39 | Site 08¦Functional Review
Site 08 | Colombia | 1 | A | UAT | 4 | 2 | 2027-05-17 | 2027-05-30 | 40 | 41 | Site 08¦UAT
Site 08 | Colombia | 1 | A | Training | 5 | 3 | 2027-05-31 | 2027-06-20 | 42 | 44 | Site 08¦Training
Site 08 | Colombia | 1 | A | DIALT | 6 | 1 | 2027-06-21 | 2027-06-27 | 45 | 45 | Site 08¦DIALT
Site 08 | Colombia | 1 | A | Go Live | 7 | 1 | 2027-06-28 | 2027-07-04 | 46 | 46 | Site 08¦Go Live
Site 08 | Colombia | 1 | A | Hypercare | 8 | 4 | 2027-07-05 | 2027-08-01 | 47 | 50 | Site 08¦Hypercare
Site 09 | Colombia | 2 | A | Site Readiness | 1 | 4 | 2027-04-19 | 2027-05-16 | 36 | 39 | Site 09¦Site Readiness
Site 09 | Colombia | 2 | A | Design Adaptation | 2 | 1 | 2027-05-17 | 2027-05-23 | 40 | 40 | Site 09¦Design Adaptation
Site 09 | Colombia | 2 | A | Functional Review | 3 | 1 | 2027-05-24 | 2027-05-30 | 41 | 41 | Site 09¦Functional Review
Site 09 | Colombia | 2 | A | UAT | 4 | 2 | 2027-05-31 | 2027-06-13 | 42 | 43 | Site 09¦UAT
Site 09 | Colombia | 2 | A | Training | 5 | 2 | 2027-06-14 | 2027-06-27 | 44 | 45 | Site 09¦Training
Site 09 | Colombia | 2 | A | DIALT | 6 | 1 | 2027-06-28 | 2027-07-04 | 46 | 46 | Site 09¦DIALT
Site 09 | Colombia | 2 | A | Go Live | 7 | 1 | 2027-07-05 | 2027-07-11 | 47 | 47 | Site 09¦Go Live
Site 09 | Colombia | 2 | A | Hypercare | 8 | 4 | 2027-07-12 | 2027-08-08 | 48 | 51 | Site 09¦Hypercare
Site 10 | Colombia | 1 | A | Site Readiness | 1 | 5 | 2027-07-19 | 2027-08-22 | 49 | 53 | Site 10¦Site Readiness
Site 10 | Colombia | 1 | A | Design Adaptation | 2 | 2 | 2027-08-23 | 2027-09-05 | 54 | 55 | Site 10¦Design Adaptation
Site 10 | Colombia | 1 | A | Functional Review | 3 | 1 | 2027-09-06 | 2027-09-12 | 56 | 56 | Site 10¦Functional Review
Site 10 | Colombia | 1 | A | UAT | 4 | 2 | 2027-09-13 | 2027-09-26 | 57 | 58 | Site 10¦UAT
Site 10 | Colombia | 1 | A | Training | 5 | 3 | 2027-09-27 | 2027-10-17 | 59 | 61 | Site 10¦Training
Site 10 | Colombia | 1 | A | DIALT | 6 | 1 | 2027-10-18 | 2027-10-24 | 62 | 62 | Site 10¦DIALT
Site 10 | Colombia | 1 | A | Go Live | 7 | 1 | 2027-10-25 | 2027-10-31 | 63 | 63 | Site 10¦Go Live
Site 10 | Colombia | 1 | A | Hypercare | 8 | 4 | 2027-11-01 | 2027-11-28 | 64 | 67 | Site 10¦Hypercare
Site 11 | Colombia | 3 | A | Site Readiness | 1 | 4 | 2027-08-02 | 2027-08-29 | 51 | 54 | Site 11¦Site Readiness
Site 11 | Colombia | 3 | A | Design Adaptation | 2 | 1 | 2027-08-30 | 2027-09-05 | 55 | 55 | Site 11¦Design Adaptation
Site 11 | Colombia | 3 | A | Functional Review | 3 | 1 | 2027-09-06 | 2027-09-12 | 56 | 56 | Site 11¦Functional Review
Site 11 | Colombia | 3 | A | UAT | 4 | 1 | 2027-09-13 | 2027-09-19 | 57 | 57 | Site 11¦UAT
Site 11 | Colombia | 3 | A | Training | 5 | 2 | 2027-09-20 | 2027-10-03 | 58 | 59 | Site 11¦Training
Site 11 | Colombia | 3 | A | DIALT | 6 | 1 | 2027-10-04 | 2027-10-10 | 60 | 60 | Site 11¦DIALT
Site 11 | Colombia | 3 | A | Go Live | 7 | 1 | 2027-10-11 | 2027-10-17 | 61 | 61 | Site 11¦Go Live
Site 11 | Colombia | 3 | A | Hypercare | 8 | 4 | 2027-10-18 | 2027-11-14 | 62 | 65 | Site 11¦Hypercare
Site 12 | Colombia | 4 | A | Site Readiness | 1 | 2 | 2027-08-09 | 2027-08-22 | 52 | 53 | Site 12¦Site Readiness
Site 12 | Colombia | 4 | A | Design Adaptation | 2 | 0 | 2027-08-23 | 2027-08-23 | 54 | 54 | Site 12¦Design Adaptation
Site 12 | Colombia | 4 | A | Functional Review | 3 | 1 | 2027-08-24 | 2027-08-30 | 54 | 55 | Site 12¦Functional Review
Site 12 | Colombia | 4 | A | UAT | 4 | 1 | 2027-08-31 | 2027-09-06 | 55 | 56 | Site 12¦UAT
Site 12 | Colombia | 4 | A | Training | 5 | 1 | 2027-09-07 | 2027-09-13 | 56 | 57 | Site 12¦Training
Site 12 | Colombia | 4 | A | DIALT | 6 | 1 | 2027-09-14 | 2027-09-20 | 57 | 58 | Site 12¦DIALT
Site 12 | Colombia | 4 | A | Go Live | 7 | 1 | 2027-09-21 | 2027-09-27 | 58 | 59 | Site 12¦Go Live
Site 12 | Colombia | 4 | A | Hypercare | 8 | 3 | 2027-09-28 | 2027-10-18 | 59 | 62 | Site 12¦Hypercare
Site 13 | Colombia | 1 | A | Site Readiness | 1 | 5 | 2027-11-29 | 2028-01-02 | 68 | 72 | Site 13¦Site Readiness
Site 13 | Colombia | 1 | A | Design Adaptation | 2 | 2 | 2028-01-03 | 2028-01-16 | 73 | 74 | Site 13¦Design Adaptation
Site 13 | Colombia | 1 | A | Functional Review | 3 | 1 | 2028-01-17 | 2028-01-23 | 75 | 75 | Site 13¦Functional Review
Site 13 | Colombia | 1 | A | UAT | 4 | 2 | 2028-01-24 | 2028-02-06 | 76 | 77 | Site 13¦UAT
Site 13 | Colombia | 1 | A | Training | 5 | 3 | 2028-02-07 | 2028-02-27 | 78 | 80 | Site 13¦Training
Site 13 | Colombia | 1 | A | DIALT | 6 | 1 | 2028-02-28 | 2028-03-05 | 81 | 81 | Site 13¦DIALT
Site 13 | Colombia | 1 | A | Go Live | 7 | 1 | 2028-03-06 | 2028-03-12 | 82 | 82 | Site 13¦Go Live
Site 13 | Colombia | 1 | A | Hypercare | 8 | 4 | 2028-03-13 | 2028-04-09 | 83 | 86 | Site 13¦Hypercare
Site 14 | Colombia | 1 | A | Site Readiness | 1 | 5 | 2027-11-15 | 2027-12-19 | 66 | 70 | Site 14¦Site Readiness
Site 14 | Colombia | 1 | A | Design Adaptation | 2 | 2 | 2027-12-20 | 2028-01-02 | 71 | 72 | Site 14¦Design Adaptation
Site 14 | Colombia | 1 | A | Functional Review | 3 | 1 | 2028-01-03 | 2028-01-09 | 73 | 73 | Site 14¦Functional Review
Site 14 | Colombia | 1 | A | UAT | 4 | 2 | 2028-01-10 | 2028-01-23 | 74 | 75 | Site 14¦UAT
Site 14 | Colombia | 1 | A | Training | 5 | 3 | 2028-01-24 | 2028-02-13 | 76 | 78 | Site 14¦Training
Site 14 | Colombia | 1 | A | DIALT | 6 | 1 | 2028-02-14 | 2028-02-20 | 79 | 79 | Site 14¦DIALT
Site 14 | Colombia | 1 | A | Go Live | 7 | 1 | 2028-02-21 | 2028-02-27 | 80 | 80 | Site 14¦Go Live
Site 14 | Colombia | 1 | A | Hypercare | 8 | 4 | 2028-02-28 | 2028-03-26 | 81 | 84 | Site 14¦Hypercare
Site 15 | Colombia | 2 | A | Site Readiness | 1 | 4 | 2027-10-18 | 2027-11-14 | 62 | 65 | Site 15¦Site Readiness
Site 15 | Colombia | 2 | A | Design Adaptation | 2 | 1 | 2027-11-15 | 2027-11-21 | 66 | 66 | Site 15¦Design Adaptation
Site 15 | Colombia | 2 | A | Functional Review | 3 | 1 | 2027-11-22 | 2027-11-28 | 67 | 67 | Site 15¦Functional Review
Site 15 | Colombia | 2 | A | UAT | 4 | 2 | 2027-11-29 | 2027-12-12 | 68 | 69 | Site 15¦UAT
Site 15 | Colombia | 2 | A | Training | 5 | 2 | 2027-12-13 | 2027-12-26 | 70 | 71 | Site 15¦Training
Site 15 | Colombia | 2 | A | DIALT | 6 | 1 | 2027-12-27 | 2028-01-02 | 72 | 72 | Site 15¦DIALT
Site 15 | Colombia | 2 | A | Go Live | 7 | 1 | 2028-01-03 | 2028-01-09 | 73 | 73 | Site 15¦Go Live
Site 15 | Colombia | 2 | A | Hypercare | 8 | 4 | 2028-01-10 | 2028-02-06 | 74 | 77 | Site 15¦Hypercare
Formulas:
Fecha Inicio = INDEX(S5:S19,MATCH([Site],P5:P19,0))
Fecha Inicio = [Fecha Fin, row above]+1
Fecha Fin = IF([Duracion (semanas)]=0,[Fecha Inicio],[Fecha Inicio]+[Duracion (semanas)]*7-1)
Inicio Site = IFERROR(IF([Prioridad]<='01_INPUTS'!$C9,'01_INPUTS'!$C7,INDEX(T5:T19,MATCH([Prioridad]-'01_INPUTS'!$C9,O5:O19,0))+1),'01_INPUTS'!$C7)
Fin Site = [Inicio Site]+[Duracion total site (sem)]*7-1

## 03_RESOURCES
ZONA DE CALCULO: detalle Site x Fase x Rol (join Schedule + Phase-Resource Allocation) - no editar
SIMULADOR WMS - 03_RESOURCES (capacidad vs demanda de recursos) | [21 empty] | Site | Fase | Rol | Consumo (capacidad) | Semana Inicio | Semana Fin | Recurso-semanas
[22 empty] | Site 01 | Site Readiness | Infrastructure Lead | 100% | 1 | 4 | 4
DISPONIBILIDAD POR ROL (fuente: 01_INPUTS) | [21 empty] | Site 01 | Site Readiness | SAP Integrations Lead | 50% | 1 | 4 | 2
Rol | Disponible (usado) | [20 empty] | Site 01 | Design Adaptation | Solution Architect | 100% | 5 | 5 | 1
Solution Architect | 1 | [20 empty] | Site 01 | Design Adaptation | SAP Integrations Lead | 50% | 5 | 5 | 0.5
Warehouse Manager Org A | 1 | [20 empty] | Site 01 | Design Adaptation | SAP Integrations Specialist | 50% | 5 | 5 | 0.5
Project Manager Country B | 1 | [20 empty] | Site 01 | Design Adaptation | Azure Lead | 50% | 5 | 5 | 0.5
Project Manager Country A | 1 | [20 empty] | Site 01 | Design Adaptation | Azure Specialist | 50% | 5 | 5 | 0.5
Change Management Lead | 2 | [20 empty] | Site 01 | Design Adaptation | Testing Lead | 100% | 5 | 5 | 1
Infrastructure Lead | 2 | [20 empty] | Site 01 | Design Adaptation | Functional Lead | 100% | 5 | 5 | 1
Functional Lead | 2 | [20 empty] | Site 01 | Design Adaptation | Trainers | 100% | 5 | 5 | 1
SAP Integrations Lead | 1 | [20 empty] | Site 01 | Design Adaptation | Infrastructure Lead | 100% | 5 | 5 | 1
SAP Integrations Specialist | 1 | [20 empty] | Site 01 | Design Adaptation | Functional Lead Vendor A | 100% | 5 | 5 | 1
Azure Lead | 1 | [20 empty] | Site 01 | Functional Review | Solution Architect | 50% | 6 | 6 | 0.5
Azure Specialist | 1 | [20 empty] | Site 01 | Functional Review | Change Management Lead | 100% | 6 | 6 | 1
Testing Lead | 1 | [20 empty] | Site 01 | Functional Review | SAP Integrations Lead | 50% | 6 | 6 | 0.5
Trainers | 1 | [20 empty] | Site 01 | Functional Review | SAP Integrations Specialist | 50% | 6 | 6 | 0.5
Functional Lead Vendor A | 2 | [20 empty] | Site 01 | Functional Review | Azure Lead | 50% | 6 | 6 | 0.5
Nota: Site 12 (Cluster 4) no tiene filas en 'Phase-Resource Allocation' en el archivo original. Su demanda de recursos se calcula en 0 (no se inventaron datos para cubrir este vacio). | [21 empty] | Site 01 | Functional Review | Azure Specialist | 50% | 6 | 6 | 0.5
[22 empty] | Site 01 | Functional Review | Testing Lead | 50% | 6 | 6 | 0.5
UTILIZACION SEMANAL POR ROL (%) - semaforo: verde <=80%, amarillo <=100%, rojo >100% (150 semanas modeladas) | [21 empty] | Site 01 | Functional Review | Functional Lead | 100% | 6 | 6 | 1
Semana | Fecha inicio semana | Solution Architect | Warehouse Manager Org A | Project Manager Country B | Project Manager Country A | Change Management Lead | Infrastructure Lead | Functional Lead | SAP Integrations Lead | SAP Integrations Specialist | Azure Lead | Azure Specialist | Testing Lead | Trainers | Functional Lead Vendor A | Support Lead | Total Requerido | Total Disponible | Utilizacion Programa % | # Roles Sobrecargados | Semaforo | Site 01 | Functional Review | Trainers | 100% | 6 | 6 | 1
1 | 2026-08-17 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | UAT | Solution Architect | 50% | 7 | 8 | 1
2 | 2026-08-24 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | UAT | Change Management Lead | 100% | 7 | 8 | 2
3 | 2026-08-31 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | UAT | SAP Integrations Lead | 50% | 7 | 8 | 1
4 | 2026-09-07 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | UAT | SAP Integrations Specialist | 50% | 7 | 8 | 1
5 | 2026-09-14 | 300% | 0% | 0% | 0% | 0% | 150% | 150% | 150% | 150% | 150% | 150% | 300% | 300% | 150% | 0% | 24 | 20 | 120% | 10 | ROJO | Site 01 | UAT | Azure Lead | 50% | 7 | 8 | 1
6 | 2026-09-21 | 150% | 0% | 0% | 0% | 150% | 0% | 150% | 150% | 150% | 150% | 150% | 150% | 300% | 0% | 0% | 18 | 20 | 90% | 9 | ROJO | Site 01 | UAT | Azure Specialist | 50% | 7 | 8 | 1
7 | 2026-09-28 | 150% | 0% | 0% | 0% | 150% | 0% | 150% | 150% | 150% | 150% | 150% | 150% | 300% | 0% | 0% | 18 | 20 | 90% | 9 | ROJO | Site 01 | UAT | Testing Lead | 50% | 7 | 8 | 1
8 | 2026-10-05 | 150% | 0% | 0% | 0% | 150% | 0% | 150% | 150% | 150% | 150% | 150% | 150% | 300% | 0% | 0% | 18 | 20 | 90% | 9 | ROJO | Site 01 | UAT | Functional Lead | 100% | 7 | 8 | 2
9 | 2026-10-12 | 0% | 0% | 0% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 300% | 0% | 0% | 6 | 20 | 30% | 2 | ROJO | Site 01 | UAT | Trainers | 100% | 7 | 8 | 2
10 | 2026-10-19 | 0% | 0% | 0% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 300% | 0% | 0% | 6 | 20 | 30% | 2 | ROJO | Site 01 | Training | Change Management Lead | 100% | 9 | 10 | 2
11 | 2026-10-26 | 150% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 225% | 225% | 0% | 300% | 150% | 0% | 18 | 20 | 90% | 7 | ROJO | Site 01 | Training | Trainers | 100% | 9 | 10 | 2
12 | 2026-11-02 | 300% | 0% | 0% | 0% | 150% | 150% | 150% | 300% | 300% | 300% | 300% | 0% | 300% | 150% | 0% | 30 | 20 | 150% | 10 | ROJO | Site 01 | DIALT | Solution Architect | 50% | 11 | 11 | 0.5
13 | 2026-11-09 | 150% | 0% | 0% | 0% | 150% | 150% | 300% | 150% | 150% | 150% | 150% | 0% | 900% | 75% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 01 | DIALT | Change Management Lead | 100% | 11 | 11 | 1
14 | 2026-11-16 | 150% | 0% | 0% | 0% | 150% | 150% | 300% | 150% | 150% | 150% | 150% | 0% | 900% | 75% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 01 | DIALT | Azure Lead | 75% | 11 | 11 | 0.75
15 | 2026-11-23 | 150% | 0% | 0% | 0% | 150% | 150% | 300% | 150% | 150% | 150% | 150% | 0% | 900% | 75% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 01 | DIALT | Azure Specialist | 75% | 11 | 11 | 0.75
16 | 2026-11-30 | 150% | 0% | 0% | 0% | 150% | 150% | 300% | 150% | 150% | 150% | 150% | 0% | 900% | 75% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 01 | DIALT | Functional Lead | 100% | 11 | 11 | 1
17 | 2026-12-07 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | DIALT | Trainers | 100% | 11 | 11 | 1
18 | 2026-12-14 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | DIALT | Functional Lead Vendor A | 100% | 11 | 11 | 1
19 | 2026-12-21 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | Go Live | Solution Architect | 100% | 12 | 12 | 1
20 | 2026-12-28 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | Go Live | Change Management Lead | 100% | 12 | 12 | 1
21 | 2027-01-04 | 200% | 0% | 0% | 0% | 0% | 150% | 100% | 150% | 100% | 100% | 100% | 200% | 200% | 100% | 0% | 17.5 | 20 | 87.5% | 5 | ROJO | Site 01 | Go Live | SAP Integrations Lead | 100% | 12 | 12 | 1
22 | 2027-01-11 | 200% | 0% | 0% | 0% | 100% | 50% | 150% | 150% | 150% | 150% | 150% | 200% | 300% | 50% | 0% | 20 | 20 | 100% | 8 | ROJO | Site 01 | Go Live | SAP Integrations Specialist | 100% | 12 | 12 | 1
23 | 2027-01-18 | 200% | 0% | 0% | 0% | 100% | 50% | 150% | 150% | 150% | 150% | 150% | 200% | 300% | 50% | 0% | 20 | 20 | 100% | 8 | ROJO | Site 01 | Go Live | Azure Lead | 100% | 12 | 12 | 1
24 | 2027-01-25 | 100% | 0% | 0% | 0% | 150% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 300% | 0% | 0% | 14 | 20 | 70% | 2 | ROJO | Site 01 | Go Live | Azure Specialist | 100% | 12 | 12 | 1
25 | 2027-02-01 | 50% | 0% | 0% | 0% | 150% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 300% | 0% | 0% | 10 | 20 | 50% | 2 | ROJO | Site 01 | Go Live | Functional Lead | 100% | 12 | 12 | 1
26 | 2027-02-08 | 100% | 0% | 0% | 0% | 150% | 0% | 100% | 50% | 50% | 125% | 125% | 50% | 300% | 50% | 0% | 14 | 20 | 70% | 4 | ROJO | Site 01 | Go Live | Trainers | 100% | 12 | 12 | 1
27 | 2027-02-15 | 150% | 0% | 0% | 0% | 150% | 50% | 100% | 100% | 100% | 175% | 175% | 0% | 300% | 100% | 0% | 18 | 20 | 90% | 5 | ROJO | Site 01 | Go Live | Infrastructure Lead | 100% | 12 | 12 | 1
28 | 2027-02-22 | 150% | 0% | 0% | 0% | 150% | 100% | 150% | 150% | 150% | 150% | 150% | 0% | 500% | 75% | 0% | 22 | 20 | 110% | 8 | ROJO | Site 01 | Go Live | Functional Lead Vendor A | 100% | 12 | 12 | 1
29 | 2027-03-01 | 100% | 0% | 0% | 0% | 150% | 100% | 200% | 100% | 100% | 100% | 100% | 0% | 700% | 50% | 0% | 22 | 20 | 110% | 3 | ROJO | Site 01 | Hypercare | Solution Architect | 50% | 13 | 16 | 2
30 | 2027-03-08 | 150% | 0% | 0% | 0% | 150% | 100% | 250% | 100% | 100% | 175% | 175% | 0% | 700% | 100% | 0% | 26 | 20 | 130% | 6 | ROJO | Site 01 | Hypercare | Change Management Lead | 100% | 13 | 16 | 4
31 | 2027-03-15 | 200% | 0% | 0% | 0% | 150% | 150% | 250% | 200% | 200% | 200% | 200% | 0% | 700% | 100% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 01 | Hypercare | SAP Integrations Lead | 50% | 13 | 16 | 2
32 | 2027-03-22 | 100% | 0% | 0% | 0% | 100% | 150% | 200% | 150% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 21.5 | 20 | 107.5% | 4 | ROJO | Site 01 | Hypercare | SAP Integrations Specialist | 50% | 13 | 16 | 2
33 | 2027-03-29 | 50% | 0% | 0% | 0% | 50% | 150% | 100% | 150% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 13 | 20 | 65% | 3 | ROJO | Site 01 | Hypercare | Azure Lead | 50% | 13 | 16 | 2
34 | 2027-04-05 | 50% | 0% | 0% | 0% | 50% | 150% | 100% | 150% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 13 | 20 | 65% | 3 | ROJO | Site 01 | Hypercare | Azure Specialist | 50% | 13 | 16 | 2
35 | 2027-04-12 | 50% | 0% | 0% | 0% | 50% | 150% | 100% | 150% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 13 | 20 | 65% | 3 | ROJO | Site 01 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
36 | 2027-04-19 | 0% | 0% | 0% | 0% | 0% | 150% | 0% | 150% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5 | 20 | 22.5% | 2 | ROJO | Site 01 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
37 | 2027-04-26 | 200% | 0% | 0% | 0% | 0% | 150% | 100% | 150% | 100% | 100% | 100% | 200% | 200% | 100% | 0% | 17.5 | 20 | 87.5% | 5 | ROJO | Site 01 | Hypercare | Trainers | 100% | 13 | 16 | 4
38 | 2027-05-03 | 150% | 0% | 0% | 0% | 50% | 100% | 100% | 150% | 100% | 100% | 100% | 150% | 200% | 50% | 0% | 15.5 | 20 | 77.5% | 4 | ROJO | Site 01 | Hypercare | Trainers | 100% | 13 | 16 | 4
39 | 2027-05-10 | 100% | 0% | 0% | 0% | 100% | 50% | 100% | 150% | 100% | 100% | 100% | 100% | 200% | 0% | 0% | 13.5 | 20 | 67.5% | 2 | ROJO | Site 01 | Hypercare | Trainers | 100% | 13 | 16 | 4
40 | 2027-05-17 | 200% | 0% | 0% | 0% | 100% | 50% | 150% | 150% | 150% | 150% | 150% | 200% | 300% | 50% | 0% | 20 | 20 | 100% | 8 | ROJO | Site 01 | Hypercare | Infrastructure Lead | 100% | 13 | 16 | 4
41 | 2027-05-24 | 100% | 0% | 0% | 0% | 150% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 300% | 0% | 0% | 14 | 20 | 70% | 2 | ROJO | Site 01 | Hypercare | Functional Lead Vendor A | 50% | 13 | 16 | 2
42 | 2027-05-31 | 50% | 0% | 0% | 0% | 150% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 300% | 0% | 0% | 10 | 20 | 50% | 2 | ROJO | Site 02 | Site Readiness | Infrastructure Lead | 100% | 1 | 4 | 4
43 | 2027-06-07 | 100% | 0% | 0% | 0% | 150% | 0% | 100% | 50% | 50% | 125% | 125% | 50% | 300% | 50% | 0% | 14 | 20 | 70% | 4 | ROJO | Site 02 | Site Readiness | SAP Integrations Lead | 50% | 1 | 4 | 2
44 | 2027-06-14 | 100% | 0% | 0% | 0% | 150% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 300% | 50% | 0% | 14 | 20 | 70% | 2 | ROJO | Site 02 | Design Adaptation | Solution Architect | 100% | 5 | 5 | 1
45 | 2027-06-21 | 100% | 0% | 0% | 0% | 150% | 50% | 150% | 50% | 50% | 125% | 125% | 0% | 500% | 75% | 0% | 18 | 20 | 90% | 5 | ROJO | Site 02 | Design Adaptation | SAP Integrations Lead | 50% | 5 | 5 | 0.5
46 | 2027-06-28 | 200% | 0% | 0% | 0% | 150% | 100% | 200% | 150% | 150% | 225% | 225% | 0% | 500% | 125% | 0% | 26 | 20 | 130% | 9 | ROJO | Site 02 | Design Adaptation | SAP Integrations Specialist | 50% | 5 | 5 | 0.5
47 | 2027-07-05 | 200% | 0% | 0% | 0% | 150% | 150% | 250% | 200% | 200% | 200% | 200% | 0% | 700% | 100% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 02 | Design Adaptation | Azure Lead | 50% | 5 | 5 | 0.5
48 | 2027-07-12 | 150% | 0% | 0% | 0% | 150% | 150% | 300% | 150% | 150% | 150% | 150% | 0% | 900% | 75% | 0% | 30 | 20 | 150% | 9 | ROJO | Site 02 | Design Adaptation | Azure Specialist | 50% | 5 | 5 | 0.5
49 | 2027-07-19 | 100% | 0% | 0% | 0% | 100% | 150% | 200% | 150% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 21.5 | 20 | 107.5% | 4 | ROJO | Site 02 | Design Adaptation | Testing Lead | 100% | 5 | 5 | 1
50 | 2027-07-26 | 100% | 0% | 0% | 0% | 100% | 150% | 200% | 150% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 21.5 | 20 | 107.5% | 4 | ROJO | Site 02 | Design Adaptation | Functional Lead | 100% | 5 | 5 | 1
51 | 2027-08-02 | 50% | 0% | 0% | 0% | 50% | 150% | 100% | 150% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 13 | 20 | 65% | 3 | ROJO | Site 02 | Design Adaptation | Trainers | 100% | 5 | 5 | 1
52 | 2027-08-09 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3 | 20 | 15% | 0 | AMARILLO | Site 02 | Design Adaptation | Infrastructure Lead | 100% | 5 | 5 | 1
53 | 2027-08-16 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3 | 20 | 15% | 0 | AMARILLO | Site 02 | Design Adaptation | Functional Lead Vendor A | 100% | 5 | 5 | 1
54 | 2027-08-23 | 100% | 0% | 0% | 0% | 0% | 100% | 50% | 100% | 50% | 50% | 50% | 100% | 100% | 50% | 0% | 9.5 | 20 | 47.5% | 0 | AMARILLO | Site 02 | Functional Review | Solution Architect | 50% | 6 | 6 | 0.5
55 | 2027-08-30 | 200% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 200% | 200% | 100% | 0% | 16 | 20 | 80% | 3 | ROJO | Site 02 | Functional Review | Change Management Lead | 100% | 6 | 6 | 1
56 | 2027-09-06 | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 200% | 0% | 0% | 12 | 20 | 60% | 1 | ROJO | Site 02 | Functional Review | SAP Integrations Lead | 50% | 6 | 6 | 0.5
57 | 2027-09-13 | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 200% | 0% | 0% | 12 | 20 | 60% | 1 | ROJO | Site 02 | Functional Review | SAP Integrations Specialist | 50% | 6 | 6 | 0.5
58 | 2027-09-20 | 50% | 0% | 0% | 0% | 100% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 200% | 0% | 0% | 8 | 20 | 40% | 1 | ROJO | Site 02 | Functional Review | Azure Lead | 50% | 6 | 6 | 0.5
59 | 2027-09-27 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 0% | 0% | 4 | 20 | 20% | 1 | ROJO | Site 02 | Functional Review | Azure Specialist | 50% | 6 | 6 | 0.5
60 | 2027-10-04 | 50% | 0% | 0% | 0% | 100% | 0% | 50% | 0% | 0% | 75% | 75% | 0% | 200% | 50% | 0% | 8 | 20 | 40% | 1 | ROJO | Site 02 | Functional Review | Testing Lead | 50% | 6 | 6 | 0.5
61 | 2027-10-11 | 100% | 0% | 0% | 0% | 100% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 200% | 50% | 0% | 12 | 20 | 60% | 1 | ROJO | Site 02 | Functional Review | Functional Lead | 100% | 6 | 6 | 1
62 | 2027-10-18 | 100% | 0% | 0% | 0% | 100% | 100% | 150% | 100% | 50% | 125% | 125% | 0% | 400% | 75% | 0% | 17.5 | 20 | 87.5% | 4 | ROJO | Site 02 | Functional Review | Trainers | 100% | 6 | 6 | 1
63 | 2027-10-25 | 150% | 0% | 0% | 0% | 100% | 150% | 150% | 200% | 150% | 150% | 150% | 0% | 400% | 75% | 0% | 21.5 | 20 | 107.5% | 8 | ROJO | Site 02 | UAT | Solution Architect | 50% | 7 | 8 | 1
64 | 2027-11-01 | 100% | 0% | 0% | 0% | 100% | 150% | 200% | 150% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 21.5 | 20 | 107.5% | 4 | ROJO | Site 02 | UAT | Change Management Lead | 100% | 7 | 8 | 2
65 | 2027-11-08 | 100% | 0% | 0% | 0% | 100% | 150% | 200% | 150% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 21.5 | 20 | 107.5% | 4 | ROJO | Site 02 | UAT | SAP Integrations Lead | 50% | 7 | 8 | 1
66 | 2027-11-15 | 150% | 0% | 0% | 0% | 50% | 150% | 150% | 150% | 100% | 100% | 100% | 100% | 400% | 75% | 0% | 19.5 | 20 | 97.5% | 5 | ROJO | Site 02 | UAT | SAP Integrations Specialist | 50% | 7 | 8 | 1
67 | 2027-11-22 | 100% | 0% | 0% | 0% | 100% | 100% | 150% | 150% | 100% | 100% | 100% | 50% | 400% | 25% | 0% | 17.5 | 20 | 87.5% | 3 | ROJO | Site 02 | UAT | Azure Lead | 50% | 7 | 8 | 1
68 | 2027-11-29 | 50% | 0% | 0% | 0% | 50% | 100% | 50% | 150% | 50% | 50% | 50% | 50% | 100% | 0% | 0% | 9 | 20 | 45% | 1 | ROJO | Site 02 | UAT | Azure Specialist | 50% | 7 | 8 | 1
69 | 2027-12-06 | 50% | 0% | 0% | 0% | 50% | 100% | 50% | 150% | 50% | 50% | 50% | 50% | 100% | 0% | 0% | 9 | 20 | 45% | 1 | ROJO | Site 02 | UAT | Testing Lead | 50% | 7 | 8 | 1
70 | 2027-12-13 | 0% | 0% | 0% | 0% | 50% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 5 | 20 | 25% | 0 | AMARILLO | Site 02 | UAT | Functional Lead | 100% | 7 | 8 | 2
71 | 2027-12-20 | 100% | 0% | 0% | 0% | 50% | 100% | 50% | 100% | 50% | 50% | 50% | 100% | 200% | 50% | 0% | 11.5 | 20 | 57.5% | 1 | ROJO | Site 02 | UAT | Trainers | 100% | 7 | 8 | 2
72 | 2027-12-27 | 150% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 50% | 125% | 125% | 100% | 200% | 100% | 0% | 15.5 | 20 | 77.5% | 4 | ROJO | Site 02 | Training | Change Management Lead | 100% | 9 | 10 | 2
73 | 2028-01-03 | 250% | 0% | 0% | 0% | 100% | 100% | 150% | 200% | 200% | 200% | 200% | 150% | 300% | 100% | 0% | 24 | 20 | 120% | 8 | ROJO | Site 02 | Training | Trainers | 100% | 9 | 10 | 2
74 | 2028-01-10 | 200% | 0% | 0% | 0% | 100% | 100% | 200% | 150% | 150% | 150% | 150% | 150% | 500% | 75% | 0% | 24 | 20 | 120% | 8 | ROJO | Site 02 | DIALT | Solution Architect | 50% | 11 | 11 | 0.5
75 | 2028-01-17 | 150% | 0% | 0% | 0% | 150% | 50% | 200% | 150% | 150% | 150% | 150% | 100% | 500% | 25% | 0% | 22 | 20 | 110% | 8 | ROJO | Site 02 | DIALT | Change Management Lead | 100% | 11 | 11 | 1
76 | 2028-01-24 | 100% | 0% | 0% | 0% | 150% | 50% | 150% | 100% | 100% | 100% | 100% | 50% | 500% | 25% | 0% | 18 | 20 | 90% | 3 | ROJO | Site 02 | DIALT | Azure Lead | 75% | 11 | 11 | 0.75
77 | 2028-01-31 | 100% | 0% | 0% | 0% | 150% | 50% | 150% | 100% | 100% | 100% | 100% | 50% | 500% | 25% | 0% | 18 | 20 | 90% | 3 | ROJO | Site 02 | DIALT | Azure Specialist | 75% | 11 | 11 | 0.75
78 | 2028-02-07 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 0% | 0% | 4 | 20 | 20% | 1 | ROJO | Site 02 | DIALT | Functional Lead | 100% | 11 | 11 | 1
79 | 2028-02-14 | 50% | 0% | 0% | 0% | 100% | 0% | 50% | 0% | 0% | 75% | 75% | 0% | 200% | 50% | 0% | 8 | 20 | 40% | 1 | ROJO | Site 02 | DIALT | Trainers | 100% | 11 | 11 | 1
80 | 2028-02-21 | 100% | 0% | 0% | 0% | 100% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 200% | 50% | 0% | 12 | 20 | 60% | 1 | ROJO | Site 02 | DIALT | Functional Lead Vendor A | 100% | 11 | 11 | 1
81 | 2028-02-28 | 100% | 0% | 0% | 0% | 100% | 50% | 150% | 50% | 50% | 125% | 125% | 0% | 400% | 75% | 0% | 16 | 20 | 80% | 4 | ROJO | Site 02 | Go Live | Solution Architect | 100% | 12 | 12 | 1
82 | 2028-03-06 | 150% | 0% | 0% | 0% | 100% | 100% | 150% | 150% | 150% | 150% | 150% | 0% | 400% | 75% | 0% | 20 | 20 | 100% | 7 | ROJO | Site 02 | Go Live | Change Management Lead | 100% | 12 | 12 | 1
83 | 2028-03-13 | 100% | 0% | 0% | 0% | 100% | 100% | 200% | 100% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 20 | 20 | 100% | 2 | ROJO | Site 02 | Go Live | SAP Integrations Lead | 100% | 12 | 12 | 1
84 | 2028-03-20 | 100% | 0% | 0% | 0% | 100% | 100% | 200% | 100% | 100% | 100% | 100% | 0% | 600% | 50% | 0% | 20 | 20 | 100% | 2 | ROJO | Site 02 | Go Live | SAP Integrations Specialist | 100% | 12 | 12 | 1
85 | 2028-03-27 | 50% | 0% | 0% | 0% | 50% | 50% | 100% | 50% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 10 | 20 | 50% | 1 | ROJO | Site 02 | Go Live | Azure Lead | 100% | 12 | 12 | 1
86 | 2028-04-03 | 50% | 0% | 0% | 0% | 50% | 50% | 100% | 50% | 50% | 50% | 50% | 0% | 300% | 25% | 0% | 10 | 20 | 50% | 1 | ROJO | Site 02 | Go Live | Azure Specialist | 100% | 12 | 12 | 1
87 | 2028-04-10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Go Live | Functional Lead | 100% | 12 | 12 | 1
88 | 2028-04-17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Go Live | Trainers | 100% | 12 | 12 | 1
89 | 2028-04-24 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Go Live | Infrastructure Lead | 100% | 12 | 12 | 1
90 | 2028-05-01 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Go Live | Functional Lead Vendor A | 100% | 12 | 12 | 1
91 | 2028-05-08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Solution Architect | 50% | 13 | 16 | 2
92 | 2028-05-15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Change Management Lead | 100% | 13 | 16 | 4
93 | 2028-05-22 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | SAP Integrations Lead | 50% | 13 | 16 | 2
94 | 2028-05-29 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | SAP Integrations Specialist | 50% | 13 | 16 | 2
95 | 2028-06-05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Azure Lead | 50% | 13 | 16 | 2
96 | 2028-06-12 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Azure Specialist | 50% | 13 | 16 | 2
97 | 2028-06-19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
98 | 2028-06-26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
99 | 2028-07-03 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Trainers | 100% | 13 | 16 | 4
100 | 2028-07-10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Trainers | 100% | 13 | 16 | 4
101 | 2028-07-17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Trainers | 100% | 13 | 16 | 4
102 | 2028-07-24 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Infrastructure Lead | 100% | 13 | 16 | 4
103 | 2028-07-31 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 02 | Hypercare | Functional Lead Vendor A | 50% | 13 | 16 | 2
104 | 2028-08-07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Site Readiness | Infrastructure Lead | 100% | 1 | 4 | 4
105 | 2028-08-14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Site Readiness | SAP Integrations Lead | 50% | 1 | 4 | 2
106 | 2028-08-21 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Solution Architect | 100% | 5 | 5 | 1
107 | 2028-08-28 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | SAP Integrations Lead | 50% | 5 | 5 | 0.5
108 | 2028-09-04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | SAP Integrations Specialist | 50% | 5 | 5 | 0.5
109 | 2028-09-11 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Azure Lead | 50% | 5 | 5 | 0.5
110 | 2028-09-18 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Azure Specialist | 50% | 5 | 5 | 0.5
111 | 2028-09-25 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Testing Lead | 100% | 5 | 5 | 1
112 | 2028-10-02 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Functional Lead | 100% | 5 | 5 | 1
113 | 2028-10-09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Trainers | 100% | 5 | 5 | 1
114 | 2028-10-16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Infrastructure Lead | 100% | 5 | 5 | 1
115 | 2028-10-23 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Design Adaptation | Functional Lead Vendor A | 100% | 5 | 5 | 1
116 | 2028-10-30 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Solution Architect | 50% | 6 | 6 | 0.5
117 | 2028-11-06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Change Management Lead | 100% | 6 | 6 | 1
118 | 2028-11-13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | SAP Integrations Lead | 50% | 6 | 6 | 0.5
119 | 2028-11-20 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | SAP Integrations Specialist | 50% | 6 | 6 | 0.5
120 | 2028-11-27 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Azure Lead | 50% | 6 | 6 | 0.5
121 | 2028-12-04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Azure Specialist | 50% | 6 | 6 | 0.5
122 | 2028-12-11 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Testing Lead | 50% | 6 | 6 | 0.5
123 | 2028-12-18 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Functional Lead | 100% | 6 | 6 | 1
124 | 2028-12-25 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Functional Review | Trainers | 100% | 6 | 6 | 1
125 | 2029-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Solution Architect | 50% | 7 | 8 | 1
126 | 2029-01-08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Change Management Lead | 100% | 7 | 8 | 2
127 | 2029-01-15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | SAP Integrations Lead | 50% | 7 | 8 | 1
128 | 2029-01-22 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | SAP Integrations Specialist | 50% | 7 | 8 | 1
129 | 2029-01-29 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Azure Lead | 50% | 7 | 8 | 1
130 | 2029-02-05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Azure Specialist | 50% | 7 | 8 | 1
131 | 2029-02-12 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Testing Lead | 50% | 7 | 8 | 1
132 | 2029-02-19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Functional Lead | 100% | 7 | 8 | 2
133 | 2029-02-26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | UAT | Trainers | 100% | 7 | 8 | 2
134 | 2029-03-05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Training | Change Management Lead | 100% | 9 | 10 | 2
135 | 2029-03-12 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Training | Trainers | 100% | 9 | 10 | 2
136 | 2029-03-19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Solution Architect | 50% | 11 | 11 | 0.5
137 | 2029-03-26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Change Management Lead | 100% | 11 | 11 | 1
138 | 2029-04-02 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Azure Lead | 75% | 11 | 11 | 0.75
139 | 2029-04-09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Azure Specialist | 75% | 11 | 11 | 0.75
140 | 2029-04-16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Functional Lead | 100% | 11 | 11 | 1
141 | 2029-04-23 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Trainers | 100% | 11 | 11 | 1
142 | 2029-04-30 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | DIALT | Functional Lead Vendor A | 100% | 11 | 11 | 1
143 | 2029-05-07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Solution Architect | 100% | 12 | 12 | 1
144 | 2029-05-14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Change Management Lead | 100% | 12 | 12 | 1
145 | 2029-05-21 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | SAP Integrations Lead | 100% | 12 | 12 | 1
146 | 2029-05-28 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | SAP Integrations Specialist | 100% | 12 | 12 | 1
147 | 2029-06-04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Azure Lead | 100% | 12 | 12 | 1
148 | 2029-06-11 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Azure Specialist | 100% | 12 | 12 | 1
149 | 2029-06-18 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Functional Lead | 100% | 12 | 12 | 1
150 | 2029-06-25 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 20 | 0% | 0 | VERDE | Site 03 | Go Live | Trainers | 100% | 12 | 12 | 1
[22 empty] | Site 03 | Go Live | Infrastructure Lead | 100% | 12 | 12 | 1
[22 empty] | Site 03 | Go Live | Functional Lead Vendor A | 100% | 12 | 12 | 1
RECURSOS POR SITE (recurso-semanas totales demandadas) | [21 empty] | Site 03 | Hypercare | Solution Architect | 50% | 13 | 16 | 2
Site | Cluster | Recurso-semanas totales | [19 empty] | Site 03 | Hypercare | Change Management Lead | 100% | 13 | 16 | 4
Site 01 | 2 | 92 | [19 empty] | Site 03 | Hypercare | SAP Integrations Lead | 50% | 13 | 16 | 2
Site 02 | 2 | 92 | [19 empty] | Site 03 | Hypercare | SAP Integrations Specialist | 50% | 13 | 16 | 2
Site 03 | 2 | 92 | [19 empty] | Site 03 | Hypercare | Azure Lead | 50% | 13 | 16 | 2
Site 04 | 2 | 92 | [19 empty] | Site 03 | Hypercare | Azure Specialist | 50% | 13 | 16 | 2
Site 05 | 3 | 86 | [19 empty] | Site 03 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
Site 06 | 1 | 103.5 | [19 empty] | Site 03 | Hypercare | Functional Lead | 100% | 13 | 16 | 4
Site 07 | 2 | 92 | [19 empty] | Site 03 | Hypercare | Trainers | 100% | 13 | 16 | 4
Site 08 | 1 | 103.5 | [19 empty] | Site 03 | Hypercare | Trainers | 100% | 13 | 16 | 4
Site 09 | 2 | 92 | [19 empty] | Site 03 | Hypercare | Trainers | 100% | 13 | 16 | 4
Site 10 | 1 | 103.5 | [19 empty] | Site 03 | Hypercare | Infrastructure Lead | 100% | 13 | 16 | 4
Site 11 | 3 | 86 | [19 empty] | Site 03 | Hypercare | Functional Lead Vendor A | 50% | 13 | 16 | 2
Site 12 | 4 | 0 | [19 empty] | Site 04 | Site Readiness | Infrastructure Lead | 100% | 17 | 20 | 4
Site 13 | 1 | 103.5 | [19 empty] | Site 04 | Site Readiness | SAP Integrations Lead | 50% | 17 | 20 | 2
Site 14 | 1 | 103.5 | [19 empty] | Site 04 | Design Adaptation | Solution Architect | 100% | 21 | 21 | 1
Site 15 | 2 | 92 | [19 empty] | Site 04 | Design Adaptation | SAP Integrations Lead | 50% | 21 | 21 | 0.5
[22 empty] | Site 04 | Design Adaptation | SAP Integrations Specialist | 50% | 21 | 21 | 0.5
|  |  |  | RECURSOS POR FASE (recurso-semanas totales, todo el programa) | [17 empty] | Site 04 | Design Adaptation | Azure Lead | 50% | 21 | 21 | 0.5
|  |  |  | Fase | Recurso-semanas totales | [16 empty] | Site 04 | Design Adaptation | Azure Specialist | 50% | 21 | 21 | 0.5
|  |  |  | Site Readiness | 91.5 | [16 empty] | Site 04 | Design Adaptation | Testing Lead | 100% | 21 | 21 | 1
|  |  |  | Design Adaptation | 152 | [16 empty] | Site 04 | Design Adaptation | Functional Lead | 100% | 21 | 21 | 1
|  |  |  | Functional Review | 84 | [16 empty] | Site 04 | Design Adaptation | Trainers | 100% | 21 | 21 | 1
|  |  |  | UAT | 156 | [16 empty] | Site 04 | Design Adaptation | Infrastructure Lead | 100% | 21 | 21 | 1
|  |  |  | Training | 66 | [16 empty] | Site 04 | Design Adaptation | Functional Lead Vendor A | 100% | 21 | 21 | 1
|  |  |  | DIALT | 84 | [16 empty] | Site 04 | Functional Review | Solution Architect | 50% | 22 | 22 | 0.5
|  |  |  | Go Live | 140 | [16 empty] | Site 04 | Functional Review | Change Management Lead | 100% | 22 | 22 | 1
|  |  |  | Hypercare | 560 | [16 empty] | Site 04 | Functional Review | SAP Integrations Lead | 50% | 22 | 22 | 0.5
[22 empty] | Site 04 | Functional Review | SAP Integrations Specialist | 50% | 22 | 22 | 0.5
CUELLOS DE BOTELLA (maxima utilizacion alcanzada por rol, todo el programa) | [21 empty] | Site 04 | Functional Review | Azure Lead | 50% | 22 | 22 | 0.5
Rol | Utilizacion maxima | Semana del pico | [19 empty] | Site 04 | Functional Review | Azure Specialist | 50% | 22 | 22 | 0.5
Solution Architect | 300% | 5 | [19 empty] | Site 04 | Functional Review | Testing Lead | 50% | 22 | 22 | 0.5
Warehouse Manager Org A | 0% | 1 | [19 empty] | Site 04 | Functional Review | Functional Lead | 100% | 22 | 22 | 1
Project Manager Country B | 0% | 1 | [19 empty] | Site 04 | Functional Review | Trainers | 100% | 22 | 22 | 1
Project Manager Country A | 0% | 1 | [19 empty] | Site 04 | UAT | Solution Architect | 50% | 23 | 24 | 1
Change Management Lead | 150% | 6 | [19 empty] | Site 04 | UAT | Change Management Lead | 100% | 23 | 24 | 2
Infrastructure Lead | 150% | 1 | [19 empty] | Site 04 | UAT | SAP Integrations Lead | 50% | 23 | 24 | 1
Functional Lead | 300% | 13 | [19 empty] | Site 04 | UAT | SAP Integrations Specialist | 50% | 23 | 24 | 1
SAP Integrations Lead | 300% | 12 | [19 empty] | Site 04 | UAT | Azure Lead | 50% | 23 | 24 | 1
SAP Integrations Specialist | 300% | 12 | [19 empty] | Site 04 | UAT | Azure Specialist | 50% | 23 | 24 | 1
Azure Lead | 300% | 12 | [19 empty] | Site 04 | UAT | Testing Lead | 50% | 23 | 24 | 1
Azure Specialist | 300% | 12 | [19 empty] | Site 04 | UAT | Functional Lead | 100% | 23 | 24 | 2
Testing Lead | 300% | 5 | [19 empty] | Site 04 | UAT | Trainers | 100% | 23 | 24 | 2
Trainers | 900% | 13 | [19 empty] | Site 04 | Training | Change Management Lead | 100% | 25 | 26 | 2
Functional Lead Vendor A | 150% | 5 | [19 empty] | Site 04 | Training | Trainers | 100% | 25 | 26 | 2
Support Lead | 0% | 1 | [19 empty] | Site 04 | DIALT | Solution Architect | 50% | 27 | 27 | 0.5
[22 empty] | Site 04 | DIALT | Change Management Lead | 100% | 27 | 27 | 1
ROL CON MAYOR CUELLO DE BOTELLA: | Trainers | Utilizacion maxima: | 900% | [18 empty] | Site 04 | DIALT | Azure Lead | 75% | 27 | 27 | 0.75
[22 empty] | Site 04 | DIALT | Azure Specialist | 75% | 27 | 27 | 0.75
[22 empty] | Site 04 | DIALT | Functional Lead | 100% | 27 | 27 | 1
[22 empty] | Site 04 | DIALT | Trainers | 100% | 27 | 27 | 1
[22 empty] | Site 04 | DIALT | Functional Lead Vendor A | 100% | 27 | 27 | 1
[22 empty] | Site 04 | Go Live | Solution Architect | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Change Management Lead | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | SAP Integrations Lead | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | SAP Integrations Specialist | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Azure Lead | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Azure Specialist | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Functional Lead | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Trainers | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Infrastructure Lead | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Go Live | Functional Lead Vendor A | 100% | 28 | 28 | 1
[22 empty] | Site 04 | Hypercare | Solution Architect | 50% | 29 | 32 | 2
[22 empty] | Site 04 | Hypercare | Change Management Lead | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | SAP Integrations Lead | 50% | 29 | 32 | 2
[22 empty] | Site 04 | Hypercare | SAP Integrations Specialist | 50% | 29 | 32 | 2
[22 empty] | Site 04 | Hypercare | Azure Lead | 50% | 29 | 32 | 2
[22 empty] | Site 04 | Hypercare | Azure Specialist | 50% | 29 | 32 | 2
[22 empty] | Site 04 | Hypercare | Functional Lead | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Functional Lead | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Trainers | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Trainers | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Trainers | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Infrastructure Lead | 100% | 29 | 32 | 4
[22 empty] | Site 04 | Hypercare | Functional Lead Vendor A | 50% | 29 | 32 | 2
[22 empty] | Site 05 | Site Readiness | Infrastructure Lead | 100% | 17 | 20 | 4
[22 empty] | Site 05 | Site Readiness | SAP Integrations Lead | 50% | 17 | 20 | 2
[22 empty] | Site 05 | Design Adaptation | Solution Architect | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Design Adaptation | SAP Integrations Lead | 50% | 21 | 21 | 0.5
[22 empty] | Site 05 | Design Adaptation | SAP Integrations Specialist | 50% | 21 | 21 | 0.5
[22 empty] | Site 05 | Design Adaptation | Azure Lead | 50% | 21 | 21 | 0.5
[22 empty] | Site 05 | Design Adaptation | Azure Specialist | 50% | 21 | 21 | 0.5
[22 empty] | Site 05 | Design Adaptation | Testing Lead | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Design Adaptation | Functional Lead | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Design Adaptation | Trainers | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Design Adaptation | Infrastructure Lead | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Design Adaptation | Functional Lead Vendor A | 100% | 21 | 21 | 1
[22 empty] | Site 05 | Functional Review | Solution Architect | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | Change Management Lead | 100% | 22 | 22 | 1
[22 empty] | Site 05 | Functional Review | SAP Integrations Lead | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | SAP Integrations Specialist | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | Azure Lead | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | Azure Specialist | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | Testing Lead | 50% | 22 | 22 | 0.5
[22 empty] | Site 05 | Functional Review | Functional Lead | 100% | 22 | 22 | 1
[22 empty] | Site 05 | Functional Review | Trainers | 100% | 22 | 22 | 1
[22 empty] | Site 05 | UAT | Solution Architect | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | Change Management Lead | 100% | 23 | 23 | 1
[22 empty] | Site 05 | UAT | SAP Integrations Lead | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | SAP Integrations Specialist | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | Azure Lead | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | Azure Specialist | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | Testing Lead | 50% | 23 | 23 | 0.5
[22 empty] | Site 05 | UAT | Functional Lead | 100% | 23 | 23 | 1
[22 empty] | Site 05 | UAT | Trainers | 100% | 23 | 23 | 1
[22 empty] | Site 05 | Training | Change Management Lead | 100% | 24 | 25 | 2
[22 empty] | Site 05 | Training | Trainers | 100% | 24 | 25 | 2
[22 empty] | Site 05 | DIALT | Solution Architect | 50% | 26 | 26 | 0.5
[22 empty] | Site 05 | DIALT | Change Management Lead | 100% | 26 | 26 | 1
[22 empty] | Site 05 | DIALT | Azure Lead | 75% | 26 | 26 | 0.75
[22 empty] | Site 05 | DIALT | Azure Specialist | 75% | 26 | 26 | 0.75
[22 empty] | Site 05 | DIALT | Functional Lead | 100% | 26 | 26 | 1
[22 empty] | Site 05 | DIALT | Trainers | 100% | 26 | 26 | 1
[22 empty] | Site 05 | DIALT | Functional Lead Vendor A | 100% | 26 | 26 | 1
[22 empty] | Site 05 | Go Live | Solution Architect | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Change Management Lead | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | SAP Integrations Lead | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | SAP Integrations Specialist | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Azure Lead | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Azure Specialist | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Functional Lead | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Trainers | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Infrastructure Lead | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Go Live | Functional Lead Vendor A | 100% | 27 | 27 | 1
[22 empty] | Site 05 | Hypercare | Solution Architect | 50% | 28 | 31 | 2
[22 empty] | Site 05 | Hypercare | Change Management Lead | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | SAP Integrations Lead | 50% | 28 | 31 | 2
[22 empty] | Site 05 | Hypercare | SAP Integrations Specialist | 50% | 28 | 31 | 2
[22 empty] | Site 05 | Hypercare | Azure Lead | 50% | 28 | 31 | 2
[22 empty] | Site 05 | Hypercare | Azure Specialist | 50% | 28 | 31 | 2
[22 empty] | Site 05 | Hypercare | Functional Lead | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Functional Lead | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Trainers | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Trainers | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Trainers | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Infrastructure Lead | 100% | 28 | 31 | 4
[22 empty] | Site 05 | Hypercare | Functional Lead Vendor A | 50% | 28 | 31 | 2
[22 empty] | Site 06 | Site Readiness | Infrastructure Lead | 100% | 17 | 21 | 5
[22 empty] | Site 06 | Site Readiness | SAP Integrations Lead | 50% | 17 | 21 | 2.5
[22 empty] | Site 06 | Design Adaptation | Solution Architect | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Design Adaptation | SAP Integrations Lead | 50% | 22 | 23 | 1
[22 empty] | Site 06 | Design Adaptation | SAP Integrations Specialist | 50% | 22 | 23 | 1
[22 empty] | Site 06 | Design Adaptation | Azure Lead | 50% | 22 | 23 | 1
[22 empty] | Site 06 | Design Adaptation | Azure Specialist | 50% | 22 | 23 | 1
[22 empty] | Site 06 | Design Adaptation | Testing Lead | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Design Adaptation | Functional Lead | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Design Adaptation | Trainers | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Design Adaptation | Infrastructure Lead | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Design Adaptation | Functional Lead Vendor A | 100% | 22 | 23 | 2
[22 empty] | Site 06 | Functional Review | Solution Architect | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | Change Management Lead | 100% | 24 | 24 | 1
[22 empty] | Site 06 | Functional Review | SAP Integrations Lead | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | SAP Integrations Specialist | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | Azure Lead | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | Azure Specialist | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | Testing Lead | 50% | 24 | 24 | 0.5
[22 empty] | Site 06 | Functional Review | Functional Lead | 100% | 24 | 24 | 1
[22 empty] | Site 06 | Functional Review | Trainers | 100% | 24 | 24 | 1
[22 empty] | Site 06 | UAT | Solution Architect | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | Change Management Lead | 100% | 25 | 26 | 2
[22 empty] | Site 06 | UAT | SAP Integrations Lead | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | SAP Integrations Specialist | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | Azure Lead | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | Azure Specialist | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | Testing Lead | 50% | 25 | 26 | 1
[22 empty] | Site 06 | UAT | Functional Lead | 100% | 25 | 26 | 2
[22 empty] | Site 06 | UAT | Trainers | 100% | 25 | 26 | 2
[22 empty] | Site 06 | Training | Change Management Lead | 100% | 27 | 29 | 3
[22 empty] | Site 06 | Training | Trainers | 100% | 27 | 29 | 3
[22 empty] | Site 06 | DIALT | Solution Architect | 50% | 30 | 30 | 0.5
[22 empty] | Site 06 | DIALT | Change Management Lead | 100% | 30 | 30 | 1
[22 empty] | Site 06 | DIALT | Azure Lead | 75% | 30 | 30 | 0.75
[22 empty] | Site 06 | DIALT | Azure Specialist | 75% | 30 | 30 | 0.75
[22 empty] | Site 06 | DIALT | Functional Lead | 100% | 30 | 30 | 1
[22 empty] | Site 06 | DIALT | Trainers | 100% | 30 | 30 | 1
[22 empty] | Site 06 | DIALT | Functional Lead Vendor A | 100% | 30 | 30 | 1
[22 empty] | Site 06 | Go Live | Solution Architect | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Change Management Lead | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | SAP Integrations Lead | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | SAP Integrations Specialist | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Azure Lead | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Azure Specialist | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Functional Lead | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Trainers | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Infrastructure Lead | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Go Live | Functional Lead Vendor A | 100% | 31 | 31 | 1
[22 empty] | Site 06 | Hypercare | Solution Architect | 50% | 32 | 35 | 2
[22 empty] | Site 06 | Hypercare | Change Management Lead | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | SAP Integrations Lead | 50% | 32 | 35 | 2
[22 empty] | Site 06 | Hypercare | SAP Integrations Specialist | 50% | 32 | 35 | 2
[22 empty] | Site 06 | Hypercare | Azure Lead | 50% | 32 | 35 | 2
[22 empty] | Site 06 | Hypercare | Azure Specialist | 50% | 32 | 35 | 2
[22 empty] | Site 06 | Hypercare | Functional Lead | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Functional Lead | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Trainers | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Trainers | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Trainers | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Infrastructure Lead | 100% | 32 | 35 | 4
[22 empty] | Site 06 | Hypercare | Functional Lead Vendor A | 50% | 32 | 35 | 2
[22 empty] | Site 07 | Site Readiness | Infrastructure Lead | 100% | 33 | 36 | 4
[22 empty] | Site 07 | Site Readiness | SAP Integrations Lead | 50% | 33 | 36 | 2
[22 empty] | Site 07 | Design Adaptation | Solution Architect | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Design Adaptation | SAP Integrations Lead | 50% | 37 | 37 | 0.5
[22 empty] | Site 07 | Design Adaptation | SAP Integrations Specialist | 50% | 37 | 37 | 0.5
[22 empty] | Site 07 | Design Adaptation | Azure Lead | 50% | 37 | 37 | 0.5
[22 empty] | Site 07 | Design Adaptation | Azure Specialist | 50% | 37 | 37 | 0.5
[22 empty] | Site 07 | Design Adaptation | Testing Lead | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Design Adaptation | Functional Lead | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Design Adaptation | Trainers | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Design Adaptation | Infrastructure Lead | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Design Adaptation | Functional Lead Vendor A | 100% | 37 | 37 | 1
[22 empty] | Site 07 | Functional Review | Solution Architect | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | Change Management Lead | 100% | 38 | 38 | 1
[22 empty] | Site 07 | Functional Review | SAP Integrations Lead | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | SAP Integrations Specialist | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | Azure Lead | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | Azure Specialist | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | Testing Lead | 50% | 38 | 38 | 0.5
[22 empty] | Site 07 | Functional Review | Functional Lead | 100% | 38 | 38 | 1
[22 empty] | Site 07 | Functional Review | Trainers | 100% | 38 | 38 | 1
[22 empty] | Site 07 | UAT | Solution Architect | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | Change Management Lead | 100% | 39 | 40 | 2
[22 empty] | Site 07 | UAT | SAP Integrations Lead | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | SAP Integrations Specialist | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | Azure Lead | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | Azure Specialist | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | Testing Lead | 50% | 39 | 40 | 1
[22 empty] | Site 07 | UAT | Functional Lead | 100% | 39 | 40 | 2
[22 empty] | Site 07 | UAT | Trainers | 100% | 39 | 40 | 2
[22 empty] | Site 07 | Training | Change Management Lead | 100% | 41 | 42 | 2
[22 empty] | Site 07 | Training | Trainers | 100% | 41 | 42 | 2
[22 empty] | Site 07 | DIALT | Solution Architect | 50% | 43 | 43 | 0.5
[22 empty] | Site 07 | DIALT | Change Management Lead | 100% | 43 | 43 | 1
[22 empty] | Site 07 | DIALT | Azure Lead | 75% | 43 | 43 | 0.75
[22 empty] | Site 07 | DIALT | Azure Specialist | 75% | 43 | 43 | 0.75
[22 empty] | Site 07 | DIALT | Functional Lead | 100% | 43 | 43 | 1
[22 empty] | Site 07 | DIALT | Trainers | 100% | 43 | 43 | 1
[22 empty] | Site 07 | DIALT | Functional Lead Vendor A | 100% | 43 | 43 | 1
[22 empty] | Site 07 | Go Live | Solution Architect | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Change Management Lead | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | SAP Integrations Lead | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | SAP Integrations Specialist | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Azure Lead | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Azure Specialist | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Functional Lead | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Trainers | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Infrastructure Lead | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Go Live | Functional Lead Vendor A | 100% | 44 | 44 | 1
[22 empty] | Site 07 | Hypercare | Solution Architect | 50% | 45 | 48 | 2
[22 empty] | Site 07 | Hypercare | Change Management Lead | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | SAP Integrations Lead | 50% | 45 | 48 | 2
[22 empty] | Site 07 | Hypercare | SAP Integrations Specialist | 50% | 45 | 48 | 2
[22 empty] | Site 07 | Hypercare | Azure Lead | 50% | 45 | 48 | 2
[22 empty] | Site 07 | Hypercare | Azure Specialist | 50% | 45 | 48 | 2
[22 empty] | Site 07 | Hypercare | Functional Lead | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Functional Lead | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Trainers | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Trainers | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Trainers | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Infrastructure Lead | 100% | 45 | 48 | 4
[22 empty] | Site 07 | Hypercare | Functional Lead Vendor A | 50% | 45 | 48 | 2
[22 empty] | Site 08 | Site Readiness | Infrastructure Lead | 100% | 32 | 36 | 5
[22 empty] | Site 08 | Site Readiness | SAP Integrations Lead | 50% | 32 | 36 | 2.5
[22 empty] | Site 08 | Design Adaptation | Solution Architect | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Design Adaptation | SAP Integrations Lead | 50% | 37 | 38 | 1
[22 empty] | Site 08 | Design Adaptation | SAP Integrations Specialist | 50% | 37 | 38 | 1
[22 empty] | Site 08 | Design Adaptation | Azure Lead | 50% | 37 | 38 | 1
[22 empty] | Site 08 | Design Adaptation | Azure Specialist | 50% | 37 | 38 | 1
[22 empty] | Site 08 | Design Adaptation | Testing Lead | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Design Adaptation | Functional Lead | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Design Adaptation | Trainers | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Design Adaptation | Infrastructure Lead | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Design Adaptation | Functional Lead Vendor A | 100% | 37 | 38 | 2
[22 empty] | Site 08 | Functional Review | Solution Architect | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | Change Management Lead | 100% | 39 | 39 | 1
[22 empty] | Site 08 | Functional Review | SAP Integrations Lead | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | SAP Integrations Specialist | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | Azure Lead | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | Azure Specialist | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | Testing Lead | 50% | 39 | 39 | 0.5
[22 empty] | Site 08 | Functional Review | Functional Lead | 100% | 39 | 39 | 1
[22 empty] | Site 08 | Functional Review | Trainers | 100% | 39 | 39 | 1
[22 empty] | Site 08 | UAT | Solution Architect | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | Change Management Lead | 100% | 40 | 41 | 2
[22 empty] | Site 08 | UAT | SAP Integrations Lead | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | SAP Integrations Specialist | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | Azure Lead | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | Azure Specialist | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | Testing Lead | 50% | 40 | 41 | 1
[22 empty] | Site 08 | UAT | Functional Lead | 100% | 40 | 41 | 2
[22 empty] | Site 08 | UAT | Trainers | 100% | 40 | 41 | 2
[22 empty] | Site 08 | Training | Change Management Lead | 100% | 42 | 44 | 3
[22 empty] | Site 08 | Training | Trainers | 100% | 42 | 44 | 3
[22 empty] | Site 08 | DIALT | Solution Architect | 50% | 45 | 45 | 0.5
[22 empty] | Site 08 | DIALT | Change Management Lead | 100% | 45 | 45 | 1
[22 empty] | Site 08 | DIALT | Azure Lead | 75% | 45 | 45 | 0.75
[22 empty] | Site 08 | DIALT | Azure Specialist | 75% | 45 | 45 | 0.75
[22 empty] | Site 08 | DIALT | Functional Lead | 100% | 45 | 45 | 1
[22 empty] | Site 08 | DIALT | Trainers | 100% | 45 | 45 | 1
[22 empty] | Site 08 | DIALT | Functional Lead Vendor A | 100% | 45 | 45 | 1
[22 empty] | Site 08 | Go Live | Solution Architect | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Change Management Lead | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | SAP Integrations Lead | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | SAP Integrations Specialist | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Azure Lead | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Azure Specialist | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Functional Lead | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Trainers | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Infrastructure Lead | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Go Live | Functional Lead Vendor A | 100% | 46 | 46 | 1
[22 empty] | Site 08 | Hypercare | Solution Architect | 50% | 47 | 50 | 2
[22 empty] | Site 08 | Hypercare | Change Management Lead | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | SAP Integrations Lead | 50% | 47 | 50 | 2
[22 empty] | Site 08 | Hypercare | SAP Integrations Specialist | 50% | 47 | 50 | 2
[22 empty] | Site 08 | Hypercare | Azure Lead | 50% | 47 | 50 | 2
[22 empty] | Site 08 | Hypercare | Azure Specialist | 50% | 47 | 50 | 2
[22 empty] | Site 08 | Hypercare | Functional Lead | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Functional Lead | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Trainers | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Trainers | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Trainers | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Infrastructure Lead | 100% | 47 | 50 | 4
[22 empty] | Site 08 | Hypercare | Functional Lead Vendor A | 50% | 47 | 50 | 2
[22 empty] | Site 09 | Site Readiness | Infrastructure Lead | 100% | 36 | 39 | 4
[22 empty] | Site 09 | Site Readiness | SAP Integrations Lead | 50% | 36 | 39 | 2
[22 empty] | Site 09 | Design Adaptation | Solution Architect | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Design Adaptation | SAP Integrations Lead | 50% | 40 | 40 | 0.5
[22 empty] | Site 09 | Design Adaptation | SAP Integrations Specialist | 50% | 40 | 40 | 0.5
[22 empty] | Site 09 | Design Adaptation | Azure Lead | 50% | 40 | 40 | 0.5
[22 empty] | Site 09 | Design Adaptation | Azure Specialist | 50% | 40 | 40 | 0.5
[22 empty] | Site 09 | Design Adaptation | Testing Lead | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Design Adaptation | Functional Lead | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Design Adaptation | Trainers | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Design Adaptation | Infrastructure Lead | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Design Adaptation | Functional Lead Vendor A | 100% | 40 | 40 | 1
[22 empty] | Site 09 | Functional Review | Solution Architect | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | Change Management Lead | 100% | 41 | 41 | 1
[22 empty] | Site 09 | Functional Review | SAP Integrations Lead | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | SAP Integrations Specialist | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | Azure Lead | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | Azure Specialist | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | Testing Lead | 50% | 41 | 41 | 0.5
[22 empty] | Site 09 | Functional Review | Functional Lead | 100% | 41 | 41 | 1
[22 empty] | Site 09 | Functional Review | Trainers | 100% | 41 | 41 | 1
[22 empty] | Site 09 | UAT | Solution Architect | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | Change Management Lead | 100% | 42 | 43 | 2
[22 empty] | Site 09 | UAT | SAP Integrations Lead | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | SAP Integrations Specialist | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | Azure Lead | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | Azure Specialist | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | Testing Lead | 50% | 42 | 43 | 1
[22 empty] | Site 09 | UAT | Functional Lead | 100% | 42 | 43 | 2
[22 empty] | Site 09 | UAT | Trainers | 100% | 42 | 43 | 2
[22 empty] | Site 09 | Training | Change Management Lead | 100% | 44 | 45 | 2
[22 empty] | Site 09 | Training | Trainers | 100% | 44 | 45 | 2
[22 empty] | Site 09 | DIALT | Solution Architect | 50% | 46 | 46 | 0.5
[22 empty] | Site 09 | DIALT | Change Management Lead | 100% | 46 | 46 | 1
[22 empty] | Site 09 | DIALT | Azure Lead | 75% | 46 | 46 | 0.75
[22 empty] | Site 09 | DIALT | Azure Specialist | 75% | 46 | 46 | 0.75
[22 empty] | Site 09 | DIALT | Functional Lead | 100% | 46 | 46 | 1
[22 empty] | Site 09 | DIALT | Trainers | 100% | 46 | 46 | 1
[22 empty] | Site 09 | DIALT | Functional Lead Vendor A | 100% | 46 | 46 | 1
[22 empty] | Site 09 | Go Live | Solution Architect | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Change Management Lead | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | SAP Integrations Lead | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | SAP Integrations Specialist | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Azure Lead | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Azure Specialist | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Functional Lead | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Trainers | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Infrastructure Lead | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Go Live | Functional Lead Vendor A | 100% | 47 | 47 | 1
[22 empty] | Site 09 | Hypercare | Solution Architect | 50% | 48 | 51 | 2
[22 empty] | Site 09 | Hypercare | Change Management Lead | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | SAP Integrations Lead | 50% | 48 | 51 | 2
[22 empty] | Site 09 | Hypercare | SAP Integrations Specialist | 50% | 48 | 51 | 2
[22 empty] | Site 09 | Hypercare | Azure Lead | 50% | 48 | 51 | 2
[22 empty] | Site 09 | Hypercare | Azure Specialist | 50% | 48 | 51 | 2
[22 empty] | Site 09 | Hypercare | Functional Lead | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Functional Lead | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Trainers | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Trainers | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Trainers | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Infrastructure Lead | 100% | 48 | 51 | 4
[22 empty] | Site 09 | Hypercare | Functional Lead Vendor A | 50% | 48 | 51 | 2
[22 empty] | Site 10 | Site Readiness | Infrastructure Lead | 100% | 49 | 53 | 5
[22 empty] | Site 10 | Site Readiness | SAP Integrations Lead | 50% | 49 | 53 | 2.5
[22 empty] | Site 10 | Design Adaptation | Solution Architect | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Design Adaptation | SAP Integrations Lead | 50% | 54 | 55 | 1
[22 empty] | Site 10 | Design Adaptation | SAP Integrations Specialist | 50% | 54 | 55 | 1
[22 empty] | Site 10 | Design Adaptation | Azure Lead | 50% | 54 | 55 | 1
[22 empty] | Site 10 | Design Adaptation | Azure Specialist | 50% | 54 | 55 | 1
[22 empty] | Site 10 | Design Adaptation | Testing Lead | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Design Adaptation | Functional Lead | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Design Adaptation | Trainers | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Design Adaptation | Infrastructure Lead | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Design Adaptation | Functional Lead Vendor A | 100% | 54 | 55 | 2
[22 empty] | Site 10 | Functional Review | Solution Architect | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | Change Management Lead | 100% | 56 | 56 | 1
[22 empty] | Site 10 | Functional Review | SAP Integrations Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | SAP Integrations Specialist | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | Azure Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | Azure Specialist | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | Testing Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 10 | Functional Review | Functional Lead | 100% | 56 | 56 | 1
[22 empty] | Site 10 | Functional Review | Trainers | 100% | 56 | 56 | 1
[22 empty] | Site 10 | UAT | Solution Architect | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | Change Management Lead | 100% | 57 | 58 | 2
[22 empty] | Site 10 | UAT | SAP Integrations Lead | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | SAP Integrations Specialist | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | Azure Lead | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | Azure Specialist | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | Testing Lead | 50% | 57 | 58 | 1
[22 empty] | Site 10 | UAT | Functional Lead | 100% | 57 | 58 | 2
[22 empty] | Site 10 | UAT | Trainers | 100% | 57 | 58 | 2
[22 empty] | Site 10 | Training | Change Management Lead | 100% | 59 | 61 | 3
[22 empty] | Site 10 | Training | Trainers | 100% | 59 | 61 | 3
[22 empty] | Site 10 | DIALT | Solution Architect | 50% | 62 | 62 | 0.5
[22 empty] | Site 10 | DIALT | Change Management Lead | 100% | 62 | 62 | 1
[22 empty] | Site 10 | DIALT | Azure Lead | 75% | 62 | 62 | 0.75
[22 empty] | Site 10 | DIALT | Azure Specialist | 75% | 62 | 62 | 0.75
[22 empty] | Site 10 | DIALT | Functional Lead | 100% | 62 | 62 | 1
[22 empty] | Site 10 | DIALT | Trainers | 100% | 62 | 62 | 1
[22 empty] | Site 10 | DIALT | Functional Lead Vendor A | 100% | 62 | 62 | 1
[22 empty] | Site 10 | Go Live | Solution Architect | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Change Management Lead | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | SAP Integrations Lead | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | SAP Integrations Specialist | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Azure Lead | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Azure Specialist | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Functional Lead | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Trainers | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Infrastructure Lead | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Go Live | Functional Lead Vendor A | 100% | 63 | 63 | 1
[22 empty] | Site 10 | Hypercare | Solution Architect | 50% | 64 | 67 | 2
[22 empty] | Site 10 | Hypercare | Change Management Lead | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | SAP Integrations Lead | 50% | 64 | 67 | 2
[22 empty] | Site 10 | Hypercare | SAP Integrations Specialist | 50% | 64 | 67 | 2
[22 empty] | Site 10 | Hypercare | Azure Lead | 50% | 64 | 67 | 2
[22 empty] | Site 10 | Hypercare | Azure Specialist | 50% | 64 | 67 | 2
[22 empty] | Site 10 | Hypercare | Functional Lead | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Functional Lead | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Trainers | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Trainers | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Trainers | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Infrastructure Lead | 100% | 64 | 67 | 4
[22 empty] | Site 10 | Hypercare | Functional Lead Vendor A | 50% | 64 | 67 | 2
[22 empty] | Site 11 | Site Readiness | Infrastructure Lead | 100% | 51 | 54 | 4
[22 empty] | Site 11 | Site Readiness | SAP Integrations Lead | 50% | 51 | 54 | 2
[22 empty] | Site 11 | Design Adaptation | Solution Architect | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Design Adaptation | SAP Integrations Lead | 50% | 55 | 55 | 0.5
[22 empty] | Site 11 | Design Adaptation | SAP Integrations Specialist | 50% | 55 | 55 | 0.5
[22 empty] | Site 11 | Design Adaptation | Azure Lead | 50% | 55 | 55 | 0.5
[22 empty] | Site 11 | Design Adaptation | Azure Specialist | 50% | 55 | 55 | 0.5
[22 empty] | Site 11 | Design Adaptation | Testing Lead | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Design Adaptation | Functional Lead | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Design Adaptation | Trainers | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Design Adaptation | Infrastructure Lead | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Design Adaptation | Functional Lead Vendor A | 100% | 55 | 55 | 1
[22 empty] | Site 11 | Functional Review | Solution Architect | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | Change Management Lead | 100% | 56 | 56 | 1
[22 empty] | Site 11 | Functional Review | SAP Integrations Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | SAP Integrations Specialist | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | Azure Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | Azure Specialist | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | Testing Lead | 50% | 56 | 56 | 0.5
[22 empty] | Site 11 | Functional Review | Functional Lead | 100% | 56 | 56 | 1
[22 empty] | Site 11 | Functional Review | Trainers | 100% | 56 | 56 | 1
[22 empty] | Site 11 | UAT | Solution Architect | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | Change Management Lead | 100% | 57 | 57 | 1
[22 empty] | Site 11 | UAT | SAP Integrations Lead | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | SAP Integrations Specialist | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | Azure Lead | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | Azure Specialist | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | Testing Lead | 50% | 57 | 57 | 0.5
[22 empty] | Site 11 | UAT | Functional Lead | 100% | 57 | 57 | 1
[22 empty] | Site 11 | UAT | Trainers | 100% | 57 | 57 | 1
[22 empty] | Site 11 | Training | Change Management Lead | 100% | 58 | 59 | 2
[22 empty] | Site 11 | Training | Trainers | 100% | 58 | 59 | 2
[22 empty] | Site 11 | DIALT | Solution Architect | 50% | 60 | 60 | 0.5
[22 empty] | Site 11 | DIALT | Change Management Lead | 100% | 60 | 60 | 1
[22 empty] | Site 11 | DIALT | Azure Lead | 75% | 60 | 60 | 0.75
[22 empty] | Site 11 | DIALT | Azure Specialist | 75% | 60 | 60 | 0.75
[22 empty] | Site 11 | DIALT | Functional Lead | 100% | 60 | 60 | 1
[22 empty] | Site 11 | DIALT | Trainers | 100% | 60 | 60 | 1
[22 empty] | Site 11 | DIALT | Functional Lead Vendor A | 100% | 60 | 60 | 1
[22 empty] | Site 11 | Go Live | Solution Architect | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Change Management Lead | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | SAP Integrations Lead | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | SAP Integrations Specialist | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Azure Lead | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Azure Specialist | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Functional Lead | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Trainers | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Infrastructure Lead | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Go Live | Functional Lead Vendor A | 100% | 61 | 61 | 1
[22 empty] | Site 11 | Hypercare | Solution Architect | 50% | 62 | 65 | 2
[22 empty] | Site 11 | Hypercare | Change Management Lead | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | SAP Integrations Lead | 50% | 62 | 65 | 2
[22 empty] | Site 11 | Hypercare | SAP Integrations Specialist | 50% | 62 | 65 | 2
[22 empty] | Site 11 | Hypercare | Azure Lead | 50% | 62 | 65 | 2
[22 empty] | Site 11 | Hypercare | Azure Specialist | 50% | 62 | 65 | 2
[22 empty] | Site 11 | Hypercare | Functional Lead | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Functional Lead | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Trainers | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Trainers | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Trainers | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Infrastructure Lead | 100% | 62 | 65 | 4
[22 empty] | Site 11 | Hypercare | Functional Lead Vendor A | 50% | 62 | 65 | 2
[22 empty] | Site 13 | Site Readiness | Infrastructure Lead | 100% | 68 | 72 | 5
[22 empty] | Site 13 | Site Readiness | SAP Integrations Lead | 50% | 68 | 72 | 2.5
[22 empty] | Site 13 | Design Adaptation | Solution Architect | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Design Adaptation | SAP Integrations Lead | 50% | 73 | 74 | 1
[22 empty] | Site 13 | Design Adaptation | SAP Integrations Specialist | 50% | 73 | 74 | 1
[22 empty] | Site 13 | Design Adaptation | Azure Lead | 50% | 73 | 74 | 1
[22 empty] | Site 13 | Design Adaptation | Azure Specialist | 50% | 73 | 74 | 1
[22 empty] | Site 13 | Design Adaptation | Testing Lead | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Design Adaptation | Functional Lead | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Design Adaptation | Trainers | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Design Adaptation | Infrastructure Lead | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Design Adaptation | Functional Lead Vendor A | 100% | 73 | 74 | 2
[22 empty] | Site 13 | Functional Review | Solution Architect | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | Change Management Lead | 100% | 75 | 75 | 1
[22 empty] | Site 13 | Functional Review | SAP Integrations Lead | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | SAP Integrations Specialist | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | Azure Lead | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | Azure Specialist | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | Testing Lead | 50% | 75 | 75 | 0.5
[22 empty] | Site 13 | Functional Review | Functional Lead | 100% | 75 | 75 | 1
[22 empty] | Site 13 | Functional Review | Trainers | 100% | 75 | 75 | 1
[22 empty] | Site 13 | UAT | Solution Architect | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | Change Management Lead | 100% | 76 | 77 | 2
[22 empty] | Site 13 | UAT | SAP Integrations Lead | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | SAP Integrations Specialist | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | Azure Lead | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | Azure Specialist | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | Testing Lead | 50% | 76 | 77 | 1
[22 empty] | Site 13 | UAT | Functional Lead | 100% | 76 | 77 | 2
[22 empty] | Site 13 | UAT | Trainers | 100% | 76 | 77 | 2
[22 empty] | Site 13 | Training | Change Management Lead | 100% | 78 | 80 | 3
[22 empty] | Site 13 | Training | Trainers | 100% | 78 | 80 | 3
[22 empty] | Site 13 | DIALT | Solution Architect | 50% | 81 | 81 | 0.5
[22 empty] | Site 13 | DIALT | Change Management Lead | 100% | 81 | 81 | 1
[22 empty] | Site 13 | DIALT | Azure Lead | 75% | 81 | 81 | 0.75
[22 empty] | Site 13 | DIALT | Azure Specialist | 75% | 81 | 81 | 0.75
[22 empty] | Site 13 | DIALT | Functional Lead | 100% | 81 | 81 | 1
[22 empty] | Site 13 | DIALT | Trainers | 100% | 81 | 81 | 1
[22 empty] | Site 13 | DIALT | Functional Lead Vendor A | 100% | 81 | 81 | 1
[22 empty] | Site 13 | Go Live | Solution Architect | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Change Management Lead | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | SAP Integrations Lead | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | SAP Integrations Specialist | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Azure Lead | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Azure Specialist | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Functional Lead | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Trainers | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Infrastructure Lead | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Go Live | Functional Lead Vendor A | 100% | 82 | 82 | 1
[22 empty] | Site 13 | Hypercare | Solution Architect | 50% | 83 | 86 | 2
[22 empty] | Site 13 | Hypercare | Change Management Lead | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | SAP Integrations Lead | 50% | 83 | 86 | 2
[22 empty] | Site 13 | Hypercare | SAP Integrations Specialist | 50% | 83 | 86 | 2
[22 empty] | Site 13 | Hypercare | Azure Lead | 50% | 83 | 86 | 2
[22 empty] | Site 13 | Hypercare | Azure Specialist | 50% | 83 | 86 | 2
[22 empty] | Site 13 | Hypercare | Functional Lead | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Functional Lead | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Trainers | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Trainers | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Trainers | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Infrastructure Lead | 100% | 83 | 86 | 4
[22 empty] | Site 13 | Hypercare | Functional Lead Vendor A | 50% | 83 | 86 | 2
[22 empty] | Site 14 | Site Readiness | Infrastructure Lead | 100% | 66 | 70 | 5
[22 empty] | Site 14 | Site Readiness | SAP Integrations Lead | 50% | 66 | 70 | 2.5
[22 empty] | Site 14 | Design Adaptation | Solution Architect | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Design Adaptation | SAP Integrations Lead | 50% | 71 | 72 | 1
[22 empty] | Site 14 | Design Adaptation | SAP Integrations Specialist | 50% | 71 | 72 | 1
[22 empty] | Site 14 | Design Adaptation | Azure Lead | 50% | 71 | 72 | 1
[22 empty] | Site 14 | Design Adaptation | Azure Specialist | 50% | 71 | 72 | 1
[22 empty] | Site 14 | Design Adaptation | Testing Lead | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Design Adaptation | Functional Lead | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Design Adaptation | Trainers | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Design Adaptation | Infrastructure Lead | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Design Adaptation | Functional Lead Vendor A | 100% | 71 | 72 | 2
[22 empty] | Site 14 | Functional Review | Solution Architect | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | Change Management Lead | 100% | 73 | 73 | 1
[22 empty] | Site 14 | Functional Review | SAP Integrations Lead | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | SAP Integrations Specialist | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | Azure Lead | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | Azure Specialist | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | Testing Lead | 50% | 73 | 73 | 0.5
[22 empty] | Site 14 | Functional Review | Functional Lead | 100% | 73 | 73 | 1
[22 empty] | Site 14 | Functional Review | Trainers | 100% | 73 | 73 | 1
[22 empty] | Site 14 | UAT | Solution Architect | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | Change Management Lead | 100% | 74 | 75 | 2
[22 empty] | Site 14 | UAT | SAP Integrations Lead | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | SAP Integrations Specialist | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | Azure Lead | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | Azure Specialist | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | Testing Lead | 50% | 74 | 75 | 1
[22 empty] | Site 14 | UAT | Functional Lead | 100% | 74 | 75 | 2
[22 empty] | Site 14 | UAT | Trainers | 100% | 74 | 75 | 2
[22 empty] | Site 14 | Training | Change Management Lead | 100% | 76 | 78 | 3
[22 empty] | Site 14 | Training | Trainers | 100% | 76 | 78 | 3
[22 empty] | Site 14 | DIALT | Solution Architect | 50% | 79 | 79 | 0.5
[22 empty] | Site 14 | DIALT | Change Management Lead | 100% | 79 | 79 | 1
[22 empty] | Site 14 | DIALT | Azure Lead | 75% | 79 | 79 | 0.75
[22 empty] | Site 14 | DIALT | Azure Specialist | 75% | 79 | 79 | 0.75
[22 empty] | Site 14 | DIALT | Functional Lead | 100% | 79 | 79 | 1
[22 empty] | Site 14 | DIALT | Trainers | 100% | 79 | 79 | 1
[22 empty] | Site 14 | DIALT | Functional Lead Vendor A | 100% | 79 | 79 | 1
[22 empty] | Site 14 | Go Live | Solution Architect | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Change Management Lead | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | SAP Integrations Lead | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | SAP Integrations Specialist | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Azure Lead | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Azure Specialist | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Functional Lead | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Trainers | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Infrastructure Lead | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Go Live | Functional Lead Vendor A | 100% | 80 | 80 | 1
[22 empty] | Site 14 | Hypercare | Solution Architect | 50% | 81 | 84 | 2
[22 empty] | Site 14 | Hypercare | Change Management Lead | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | SAP Integrations Lead | 50% | 81 | 84 | 2
[22 empty] | Site 14 | Hypercare | SAP Integrations Specialist | 50% | 81 | 84 | 2
[22 empty] | Site 14 | Hypercare | Azure Lead | 50% | 81 | 84 | 2
[22 empty] | Site 14 | Hypercare | Azure Specialist | 50% | 81 | 84 | 2
[22 empty] | Site 14 | Hypercare | Functional Lead | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Functional Lead | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Trainers | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Trainers | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Trainers | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Infrastructure Lead | 100% | 81 | 84 | 4
[22 empty] | Site 14 | Hypercare | Functional Lead Vendor A | 50% | 81 | 84 | 2
[22 empty] | Site 15 | Site Readiness | Infrastructure Lead | 100% | 62 | 65 | 4
[22 empty] | Site 15 | Site Readiness | SAP Integrations Lead | 50% | 62 | 65 | 2
[22 empty] | Site 15 | Design Adaptation | Solution Architect | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Design Adaptation | SAP Integrations Lead | 50% | 66 | 66 | 0.5
[22 empty] | Site 15 | Design Adaptation | SAP Integrations Specialist | 50% | 66 | 66 | 0.5
[22 empty] | Site 15 | Design Adaptation | Azure Lead | 50% | 66 | 66 | 0.5
[22 empty] | Site 15 | Design Adaptation | Azure Specialist | 50% | 66 | 66 | 0.5
[22 empty] | Site 15 | Design Adaptation | Testing Lead | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Design Adaptation | Functional Lead | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Design Adaptation | Trainers | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Design Adaptation | Infrastructure Lead | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Design Adaptation | Functional Lead Vendor A | 100% | 66 | 66 | 1
[22 empty] | Site 15 | Functional Review | Solution Architect | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | Change Management Lead | 100% | 67 | 67 | 1
[22 empty] | Site 15 | Functional Review | SAP Integrations Lead | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | SAP Integrations Specialist | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | Azure Lead | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | Azure Specialist | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | Testing Lead | 50% | 67 | 67 | 0.5
[22 empty] | Site 15 | Functional Review | Functional Lead | 100% | 67 | 67 | 1
[22 empty] | Site 15 | Functional Review | Trainers | 100% | 67 | 67 | 1
[22 empty] | Site 15 | UAT | Solution Architect | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | Change Management Lead | 100% | 68 | 69 | 2
[22 empty] | Site 15 | UAT | SAP Integrations Lead | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | SAP Integrations Specialist | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | Azure Lead | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | Azure Specialist | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | Testing Lead | 50% | 68 | 69 | 1
[22 empty] | Site 15 | UAT | Functional Lead | 100% | 68 | 69 | 2
[22 empty] | Site 15 | UAT | Trainers | 100% | 68 | 69 | 2
[22 empty] | Site 15 | Training | Change Management Lead | 100% | 70 | 71 | 2
[22 empty] | Site 15 | Training | Trainers | 100% | 70 | 71 | 2
[22 empty] | Site 15 | DIALT | Solution Architect | 50% | 72 | 72 | 0.5
[22 empty] | Site 15 | DIALT | Change Management Lead | 100% | 72 | 72 | 1
[22 empty] | Site 15 | DIALT | Azure Lead | 75% | 72 | 72 | 0.75
[22 empty] | Site 15 | DIALT | Azure Specialist | 75% | 72 | 72 | 0.75
[22 empty] | Site 15 | DIALT | Functional Lead | 100% | 72 | 72 | 1
[22 empty] | Site 15 | DIALT | Trainers | 100% | 72 | 72 | 1
[22 empty] | Site 15 | DIALT | Functional Lead Vendor A | 100% | 72 | 72 | 1
[22 empty] | Site 15 | Go Live | Solution Architect | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Change Management Lead | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | SAP Integrations Lead | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | SAP Integrations Specialist | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Azure Lead | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Azure Specialist | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Functional Lead | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Trainers | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Infrastructure Lead | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Go Live | Functional Lead Vendor A | 100% | 73 | 73 | 1
[22 empty] | Site 15 | Hypercare | Solution Architect | 50% | 74 | 77 | 2
[22 empty] | Site 15 | Hypercare | Change Management Lead | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | SAP Integrations Lead | 50% | 74 | 77 | 2
[22 empty] | Site 15 | Hypercare | SAP Integrations Specialist | 50% | 74 | 77 | 2
[22 empty] | Site 15 | Hypercare | Azure Lead | 50% | 74 | 77 | 2
[22 empty] | Site 15 | Hypercare | Azure Specialist | 50% | 74 | 77 | 2
[22 empty] | Site 15 | Hypercare | Functional Lead | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Functional Lead | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Trainers | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Trainers | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Trainers | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Infrastructure Lead | 100% | 74 | 77 | 4
[22 empty] | Site 15 | Hypercare | Functional Lead Vendor A | 50% | 74 | 77 | 2

## 04_COSTS
SIMULADOR WMS - 04_COSTS (costos e indicadores financieros del escenario)
Nota: los costos de sitios (Financials (USD)) estan en USD y los costos de recursos (Resource Master) estan en MXN en los datos originales. No existe un tipo de cambio en el archivo fuente, por lo que no se combinan ambas monedas en un solo total (se muestran por separado para no inventar una tasa de conversion).
COSTO POR SITE (USD) - fuente: Financials (USD), segun etiquetado/WiFi elegidos en 01_INPUTS
Site | Pais | Cluster | Costo base (sin etiquetado/WiFi) | Costo etiquetado elegido | Costo WiFi elegido | Costo total site (USD) | Beneficio mensual (USD)
Site 01 | Mexico | 2 | 47464.3204 | 7144.76 | 44451 | 99060.0804 | 18511
Site 02 | Mexico | 2 | 143424.8151 | 81930.072 | 287249 | 512603.8871 | 26878
Site 03 | Mexico | 2 | 162848.3568 | 212307.9 | 378909 | 754065.2568 | 61087
Site 04 | Mexico | 2 | 206112.706 | 184000.18 | 411279 | 801391.886 | 70898
Site 05 | Mexico | 3 | 43142.561 | 73600.072 | 219880 | 336622.633 | 14809
Site 06 | Mexico | 1 | 369764.5588 | 302730.288 | 523835 | 1196329.8468 | 76636
Site 07 | Mexico | 2 | 189431.2487 | 147200.144 | 277152 | 613783.3927 | 30543
Site 08 | Colombia | 1 | 50000 | 0 | 0 | 50000 | 70420
Site 09 | Colombia | 2 | 34747 | 0 | 133781 | 168528 | 15920
Site 10 | Colombia | 1 | 106583 | 308459.6755 | 487872 | 902914.6755 | 90320
Site 11 | Colombia | 3 | 40333 | 176263 | 180753 | 397349 | 24480
Site 12 | Colombia | 4 | 11986 | 88131 | 116598 | 216715 | 10180
Site 13 | Colombia | 1 | 557721 | 1189773 | 333663 | 2081157 | 109140
Site 14 | Colombia | 1 | 121140 | 925379 | 319639 | 1366158 | 56820
Site 15 | Colombia | 2 | 44271 | 88131 | 139767 | 272169 | 27560
TOTAL PROGRAMA | [5 empty] | 9768847.6583 | 704202
COSTO POR RECURSO (MXN) - fuente: Resource Master. Supuesto: cada recurso disponible se asume contratado toda la duracion del programa.
Rol | Disponible (usado) | Costo mensual promedio (MXN) | Duracion del programa (meses) | Costo total del rol (MXN)
Solution Architect | 1 | 36000 | 19.7929 | 712543.153
Warehouse Manager Org A | 1 | 35000 | 19.7929 | 692750.2877
Project Manager Country B | 1 | 25000 | 19.7929 | 494821.6341
Project Manager Country A | 1 | 25000 | 19.7929 | 494821.6341
Change Management Lead | 2 | 16000 | 19.7929 | 633371.6916
Infrastructure Lead | 2 | 42500 | 19.7929 | 1682393.5558
Functional Lead | 2 | 35000 | 19.7929 | 1385500.5754
SAP Integrations Lead | 1 | 62000 | 19.7929 | 1227157.6525
SAP Integrations Specialist | 1 | 55000 | 19.7929 | 1088607.5949
Azure Lead | 1 | 48000 | 19.7929 | 950057.5374
Azure Specialist | 1 | 45000 | 19.7929 | 890678.9413
Testing Lead | 1 | 35000 | 19.7929 | 692750.2877
Trainers | 1 | 28000 | 19.7929 | 554200.2301
Functional Lead Vendor A | 2 | 36000 | 19.7929 | 1425086.3061
Support Lead | 2 | 22000 | 19.7929 | 870886.0759
TOTAL RECURSOS (MXN) |  |  |  | 13795627.1577
RESUMEN FINANCIERO DEL PROGRAMA
Costo total de implementacion (USD): | 9768847.6583
Costo total de recursos (MXN): | 13795627.1577
Beneficio mensual total (USD): | 704202
Payback en meses (USD implementacion / beneficio mensual USD): | 13.8722
Payback en anios: | 1.156

## 05_DASHBOARD
SIMULADOR WMS - 05_DASHBOARD (panel ejecutivo)
Escenario: Escenario Base ¦ Deployment Maturity: A ¦ Max. sites en paralelo: 3
DURACION TOTAL (MESES) |  | OBJETIVO (MESES) |  | CUMPLE OBJETIVO? |  | NUMERO DE SITES | COSTO IMPLEMENTACION | COSTO RECURSOS | BENEFICIO MENSUAL | PAYBACK (MESES) | RECURSOS SOBRECARGADOS
19.7929 |  | 8 |  | NO CUMPLE |  | 15 | 9768847.6583 | 13795627.1577 | 704202 | 13.8722 | 11
SEMAFORO EJECUTIVO: | ROJO - no cumple 8 meses
GANTT GENERAL DEL PROGRAMA (todos los Sites, en dias desde el inicio)
Site | Inicio (dias offset) | Duracion (dias) | Fecha inicio | Fecha fin
Site 01 | 0 | 112 | 2026-08-17 | 2026-12-06
Site 02 | 0 | 112 | 2026-08-17 | 2026-12-06
Site 03 | 0 | 112 | 2026-08-17 | 2026-12-06
Site 04 | 112 | 112 | 2026-12-07 | 2027-03-28
Site 05 | 112 | 105 | 2026-12-07 | 2027-03-21
Site 06 | 112 | 133 | 2026-12-07 | 2027-04-18
Site 07 | 224 | 112 | 2027-03-29 | 2027-07-18
Site 08 | 217 | 133 | 2027-03-22 | 2027-08-01
Site 09 | 245 | 112 | 2027-04-19 | 2027-08-08
Site 10 | 336 | 133 | 2027-07-19 | 2027-11-28
Site 11 | 350 | 105 | 2027-08-02 | 2027-11-14
Site 12 | 357 | 70 | 2027-08-09 | 2027-10-17
Site 13 | 469 | 133 | 2027-11-29 | 2028-04-09
Site 14 | 455 | 133 | 2027-11-15 | 2028-03-26
Site 15 | 427 | 112 | 2027-10-18 | 2028-02-06
Limite objetivo (dias): | 243.52
ESCENARIO OPTIMO - menor costo posible cumpliendo <= 8 meses (busqueda sobre variables existentes del simulador)
Encontrado evaluando 54 combinaciones de Deployment Maturity, Max. Sites en paralelo (con headcount minimo sin sobrecarga en cada una) y verificacion local con reordenamiento de prioridad de sites. No modifica el Escenario Actual (01_INPUTS); queda guardado como fila en 07_SCENARIOS.
ESCENARIO OPTIMO |  | DURACION TOTAL (SEMANAS) |  | DURACION (MESES) |  | COSTO IMPLEMENTACION (USD) | COSTO RECURSOS (MXN) | CUMPLE 8 MESES?
A |  | 19 |  | 4.3728 |  | 4991382.519 | 24831185.2704 | CUMPLE
AHORRO EN IMPLEMENTACION (USD) vs Escenario Actual |  | RECURSOS REQUERIDOS (headcount total) |  | UTILIZACION MAXIMA DE RECURSOS |  | PAYBACK (MESES) | ROLES SOBRECARGADOS | COSTO RECURSOS ESCENARIO ACTUAL (MXN, referencia)
4777465.1392 |  | 154.5 |  | 100% |  | 7.088 | 0 | 13795627.1577
CONFIGURACION GANADORA
Variable | Valor optimo
Deployment Maturity | A
Max. Sites en paralelo | 15
Metodo de etiquetado | Manual Labeling
Estrategia de WiFi | WiFi Prioritized
Solution Architect | 9.5 personas
Functional Lead | 24 personas
Project Manager Country A | 0 personas
Project Manager Country B | 0 personas
Infrastructure Lead | 14 personas
SAP Integrations Lead | 9.5 personas
Azure Lead | 9.5 personas
Otros recursos existentes | Warehouse Manager Org A: 0 ¦ Change Management Lead: 14 ¦ SAP Integrations Specialist: 9.5 ¦ Azure Specialist: 9.5 ¦ Testing Lead: 9.5 ¦ Trainers: 36 ¦ Functional Lead Vendor A: 9.5 ¦ Support Lead: 0
GANTT DEL ESCENARIO OPTIMO (todos los sites inician en paralelo)
Site | Inicio (dias offset) | Duracion (dias)
Site 01 | 0 | 112
Site 02 | 0 | 112
Site 03 | 0 | 112
Site 04 | 0 | 112
Site 05 | 0 | 105
Site 06 | 0 | 133
Site 07 | 0 | 112
Site 08 | 0 | 133
Site 09 | 0 | 112
Site 10 | 0 | 133
Site 11 | 0 | 105
Site 12 | 0 | 70
Site 13 | 0 | 133
Site 14 | 0 | 133
Site 15 | 0 | 112
COSTO POR SITE - ESCENARIO OPTIMO (USD) |  |  | COSTO POR RECURSO - ESCENARIO OPTIMO (MXN)
Site | Costo (USD) |  | Rol | Disponible | Costo mensual (MXN) | Costo total (MXN)
Site 01 | 47464.3204 |  | Solution Architect | 9.5 | 36000 | 1495512.0829
Site 02 | 396471.0178 |  | Warehouse Manager Org A | 0 | 35000 | 0
Site 03 | 534979.2449 |  | Project Manager Country B | 0 | 25000 | 0
Site 04 | 657224.4965 |  | Project Manager Country A | 0 | 25000 | 0
Site 05 | 224362.7198 |  | Change Management Lead | 14 | 16000 | 979516.6858
Site 06 | 966325.9602 |  | Infrastructure Lead | 14 | 42500 | 2601841.1968
Site 07 | 465773.6395 |  | Functional Lead | 24 | 35000 | 3673187.5719
Site 08 | 50000 |  | SAP Integrations Lead | 9.5 | 62000 | 2575604.1427
Site 09 | 135609 |  | SAP Integrations Specialist | 9.5 | 55000 | 2284810.1266
Site 10 | 261528.835 |  | Azure Lead | 9.5 | 48000 | 1994016.1105
Site 11 | 134906.8118 |  | Azure Specialist | 9.5 | 45000 | 1869390.1036
Site 12 | 55628.3158 |  | Testing Lead | 9.5 | 35000 | 1453970.0806
Site 13 | 694270.4177 |  | Trainers | 36 | 28000 | 4407825.0863
Site 14 | 242636.1046 |  | Functional Lead Vendor A | 9.5 | 36000 | 1495512.0829
Site 15 | 124201.6351 |  | Support Lead | 0 | 22000 | 0
TOTAL | 4991382.519 |  | TOTAL |  |  | 24831185.2704
COSTO TOTAL - ESCENARIO OPTIMO
Costo implementacion (USD): | 4991382.519
Costo recursos (MXN): | 24831185.2704
Formulas:
Fecha inicio = INDEX('02_SCHEDULE'!$S5:S19,MATCH([DURACION TOTAL (MESES)],'02_SCHEDULE'!$P5:P19,0))
CUMPLE OBJETIVO? = INDEX('02_SCHEDULE'!$T5:T19,MATCH([DURACION TOTAL (MESES)],'02_SCHEDULE'!$P5:P19,0))
Limite 8 meses

## 06_SITE_VIEW
SIMULADOR WMS - 06_SITE_VIEW (detalle por Site)
Seleccionar Site: | Site 01
CRONOGRAMA Y FINANCIERO
Pais | Mexico | Duracion (semanas) | 16
Cluster | 2 | Fecha inicio | 2026-08-17
Capacidad (Mio HL) | 3.72 | Fecha fin | 2026-12-06
Produccion (Mio HL) | 1.43 | Costo total del site (USD) | 99060.0804
Volumen distribucion (K HL) | 6400 | Beneficio mensual (USD) | 18511
# Bodegas (Warehouses) | 1 | Payback del site (meses) | 5.3514
Area de bodega | 9100 | Recurso-semanas totales | 92
Control Tower | No
Estado WIFI | 85%
Tablets | 15
RECURSOS USADOS POR EL SITE (recurso-semanas por rol)
Rol | Recurso-semanas
Solution Architect | 6
Warehouse Manager Org A | 0
Project Manager Country B | 0
Project Manager Country A | 0
Change Management Lead | 11
Infrastructure Lead | 10
Functional Lead | 14
SAP Integrations Lead | 7
SAP Integrations Specialist | 5
Azure Lead | 5.75
Azure Specialist | 5.75
Testing Lead | 2.5
Trainers | 20
Functional Lead Vendor A | 5
Support Lead | 0
|  | GANTT DE FASES DEL SITE SELECCIONADO |  |  |  |  | fila base (uso interno):
|  | Fase | Inicio (dias offset del site) | Duracion (dias) | Fecha inicio | Fecha fin | 5
|  | Site Readiness | 0 | 28 | 2026-08-17 | 2026-09-13
|  | Design Adaptation | 28 | 7 | 2026-09-14 | 2026-09-20
|  | Functional Review | 35 | 7 | 2026-09-21 | 2026-09-27
|  | UAT | 42 | 14 | 2026-09-28 | 2026-10-11
|  | Training | 56 | 14 | 2026-10-12 | 2026-10-25
|  | DIALT | 70 | 7 | 2026-10-26 | 2026-11-01
|  | Go Live | 77 | 7 | 2026-11-02 | 2026-11-08
|  | Hypercare | 84 | 28 | 2026-11-09 | 2026-12-06

## 07_SCENARIOS
SIMULADOR WMS - 07_SCENARIOS (guardar y comparar escenarios)
Como guardar un escenario: ajuste los inputs en 01_INPUTS, revise 05_DASHBOARD, luego copie la fila 'ESCENARIO ACTUAL (en vivo)' de abajo y peguela como VALORES (Ctrl+Alt+V > Valores) en una fila 'Escenario guardado'. El archivo es .xlsx sin macros, por eso el guardado es manual.
Nombre | Deployment Maturity | Recursos (resumen) | Duracion total (meses) | Costo implementacion (USD) | Beneficio mensual (USD) | Payback (meses) | Cumple 8 meses? | Roles sobrecargados | Principal cuello de botella | Costo Recursos (MXN)
ESCENARIO ACTUAL (en vivo): Escenario Base | A | Fuente:Actual ¦ Max.Paralelo:3 ¦ Etiquetado:Label Printers / Labelers ¦ WiFi:WiFi Full | 19.7929 | 9768847.6583 | 704202 | 13.8722 | NO CUMPLE | 11 | Trainers (900%) | 13795627.1577
ESCENARIO OPTIMO (busqueda: 54 combinaciones evaluadas) | A | Fuente:Actual+ajuste manual (headcount minimo sin sobrecarga) ¦ Max.Paralelo:15 ¦ Etiquetado:Manual Labeling ¦ WiFi:WiFi Prioritized | 4.3728 | 4991382.519 | 704202 | 7.088 | CUMPLE | 0 | Solution Architect (100%) | 24831185.2704
(vacio - pegue aqui un escenario guardado)
(vacio - pegue aqui un escenario guardado)
(vacio - pegue aqui un escenario guardado)
(vacio - pegue aqui un escenario guardado)
ESCENARIO RECOMENDADO
Escenarios que cumplen <= 8 meses: | 1
Escenario recomendado (cumple 8 meses y menor costo): | ESCENARIO OPTIMO (busqueda: 54 combinaciones evaluadas)
Costo del escenario recomendado (USD): | 4991382.519